## Previous Mitigation Actions
Action # | Action Title | Action Description | Mitigation Goal | Mitigation Category | Hazard(s) Addressed | Estimated Cost | Potential Funding Source | Lead Department | Implementation Schedule | Priority Score | Priority | Current Status | Status Description / Explanation | Keep for Updated Plan? | Updated Action Title/Description (if applicable)
1 | Evaluate current bylaws and regulations regarding floodplain development to ensure they are consistent and updated | Review zoning bylaw, wetlands bylaw, building code, and health & safety regulations in order to ensure consistency across the regulations and most modern information is included. Could additionally leverage technical assistance via a consultant. | TBD |  |  | Working Group/Town staff | Working Group/Town staff | N/A | Working Group/Town staff | 28.4 |  | Delayed | Due to limited planning staff this has not progressed, however, now that we have a new Planning Director, this is on the list of projects for the next few years. | YES - updated/revised description provided at right, if applicable | Renamed to "Evaluate and enhance current ordinances and regulations regarding floodplain development."
2 | Purchase & install 4 automated weather stations | Purchase and install 4 automated weather stations throughout Town, with web-based access. Weather stations will assist DPW personnel with assessing storms to improve response to extreme precipitation, high winds, and winter storms. They will also assist Police & Fire with emergency response for storm events. | TBD |  |  | 10000 | Operating budget; FEMA funding | DPW | Short | 27.6 |  | In Progress | We should consider the use of this term- 'Delayed'. We would like to eventually have this capability but currently do not have funding. | YES - updated/revised description provided at right, if applicable | Integrated into: "Purchase & install automated weather stations and additional pavement sensors."
3 | Integrate flood storage review into open space plan | Purchase and install 4 automated weather stations throughout Town, with web-based access. Weather stations will assist DPW personnel with assessing storms to improve response to extreme precipitation, high winds, and winter storms. They will also assist Police & Fire with emergency response for storm events. | TBD |  |  | Working Group/Town staff | Working Group/Town staff | N/A | Working Group/Town staff | 27.4 |  | In Progress | This is mentioned in the 2020 OSRP but the OSRP has not been finalized at this time due to staffing constraints and high staff turnover. | YES - updated/revised description provided at right, if applicable | Carried directly into HMP Update.
4 | Install additional stream gauges | Install additional automated stream gauges (surface water level sensors and communications equipment) at high risk areas. Angelica Drive (Angelica Brook) Bates Rd (Beaver Dam Brook) | TBD |  |  | $15,000-$30,000/each | Capital budget; FEMA funding | DPW | Medium | 26.8 |  | In Progress | Ongoing as funding allows. We recently acquired new stream gauges and are in the process of installing them. The selected locations have been revised. Keep on the list because we would like to add more as funding allows. DPW replaced four existing stream gauges in July 2018 with upgraded technology with web portal. Transparency forthcoming. | YES - updated/revised description provided at right, if applicable | Integrated into: "Purchase & install automated weather stations and additional pavement sensors."
5 | Enhance current bylaws and regulations to prevent future development in the floodplain | Review Planning & Wetlands bylaws in regards to allowable development in floodplains. Currently, development is not prohibited, but mitigation is needed. Bylaw revisions need to be approved at Town Meeting. This is one of the activities to get credit for the CRS program. | TBD |  |  | Working Group/Town staff | Working Group/Town staff | N/A | Working Group/Town staff | 26.8 |  | In Progress | Due to limited planning staff this has not progressed, however, now that we have a new Planning Director, this is on the list of projects for the next few years. | YES - updated/revised description provided at right, if applicable | Carried directly into HMP Update.
6 | Install additional pavement sensors | The DPW Highway Department use pavement sensors to evaluate the temperature of pavement during cold weather. This data enables the Highway Department to identify roads for pretreatment which reduces roadway icing and other hazards associated with winter storms. | TBD |  |  | 20000 | Operating budget; FEMA funding | DPW | Short | 26.4 |  | In Progress | DPW Highway installed a couple sensors, however, were difficult to maintain, and expensive. No current funding available. Low priority. | YES - updated/revised description provided at right, if applicable | Integrated into: "Purchase & install automated weather stations and additional pavement sensors."
7 | Develop stormwater bylaw & regulations | Develop bylaws for stormwater management for new and re- development within Town. | TBD |  |  | Working Group/Town staff | Working Group/Town staff | N/A | Working Group/Town staff | 26.4 |  | Completed | COMPLETE - **Current updates comply with MS4 but might need further improvemets to reduce current flooding problems | NO - explanation provided at left | Completed, not incorporated into update.
8 | Develop green infrastructure bylaw & regulations | Develop bylaws for green infrastructure for new and re- development within Town. Could additionally leverage technical assistance via a consultant. Note: the NPDES MS4 permit will require the Town to assess local regulations regarding green infrastructure by 2021. |  |  |  | Working Group/Town staff | Working Group/Town staff | N/A | Working Group/Town staff | 26.2 |  | Completed | COMPLETE – Current regulations were reviewed by VHB and MassAudubon and subsequent bylaws have been updated (Subdivision Rules and Regs, Zoning Bylaw, etc.) | NO - explanation provided at left | Completed, not incorporated into update.
9 | Emergency generators for traffic signals | Power can be lost during winter storm events or high winds, including power used for traffic signals. For example, during a 2013 storm event, power was lost at a major intersection's traffic signal for 6 days. Police details were required, pulling limited emergency personnel from other weather-related emergencies. Loss of power to traffic signals compounds hazardous travel conditions. Emergency, back-up generators for traffic signals will help facilitate traffic flow and mitigate hazardous conditions. |  |  |  | 10000 | Operating budget; FEMA funding | DPW/Police | Medium | 26.2 |  | Delayed | Potentially bundle these into one capital project for FY20 or FY21. KR to discuss with DPW. | YES - updated/revised description provided at right, if applicable | Carried directly into HMP Update.
10 | Conduct a Climate Change Vulnerability Assessment | The Climate Change Vulnerability Assessment would help the Town understand how we are vulnerable or resilient to potential climate change in terms of impacts on people, infrastructure, public health, and the economy. It would serve as the technical reference for identifying and planning mitigation projects. The Town would also use it to revise Town regulations for private development to improve resiliency. |  |  |  | $75,000-$100,000 | FEMA funding | C&ED/DPW | Long | 26 |  | Completed & Expanded Upon | In progress. City was awarded funding under the MVP Program in 2018. Fuss & O’Neill conduct a climate change analysis. City to begin Climate Action Planning with the central goal of establishing long-term strategies and actions to reduce local greenhouse gas emissions. The focus on the plan will be less on natural hazards and more so in mitigating the City's contribution to greenhouse gas emissions and identifying opportunities to advance the long-term social, economic, and enviornmental health of the community. | YES - updated/revised description provided at right, if applicable | Completed, not incorporated into update. Tangentially incorporated into "Integrate relevant hazard mitigation plan priorities and actions into the City's forthcoming Climate Action Plan."
11 | Culvert replacement at CSX crossing of Hop Brook | Feasibility of a culvert replacement will be analyzed as part of the Landham Pond Dam Removal project. The culvert will be rehabilitated or replaced to increase capacity and meet stream crossing standards. Would require site control/CSX corridor acquisition. |  |  |  | $1.5M | FEMA funding | DPW | Long | 26 |  | In Progress | DPW secured $150K DER grant funding to study the replacement of the City-owned Colonial Drive culvert which is the last culvert downstream of the CSX culverts and will need to be upgraded before the CSX culverts can be upgraded. Anticipated June 2019 | YES - updated/revised description provided at right, if applicable | Integrated into: "Acquire the CSX Corridor and implement next steps to develop the Bruce Freeman Rail Trail."
12 | Prepare, adopt, implement, and update a comprehensive flood hazard mitigation plan | Use standard planning process (similar to the MHMP process) to develop plan. Plan would need to be approved by Board of Selectmen. Updates would be required every 5 years. This is a minimum requirement for the CRS program for all repetitive loss communities. |  |  |  | 50000 | FEMA funding; Administrative | C&ED/DPW | Medium | 26 |  | Delayed | Due to limited planning staff this has not progressed, however, now that we have a new Planning Director, this is on the list of projects for the next few years. | YES - updated/revised description provided at right, if applicable | Removed.
13 | Complete Stormwater Master Plan Phase IV | Phase IV will continue the study of the Town’s stormwater system. Five of the Town’s twenty-two sub-basins will be studied as part of this project: North and South Saxonville, Cherry Meadow Brook, Birch Meadow Brook and Baiting Brook drainage sub-basins. |  |  |  | 450000 | Capital budget | DPW | Medium | 25.8 |  | Delayed | Rather than Phase IV and V, there is a request for a Comprehensive Stormwater Master Plan that would incorporate Phases IV and V but also revisit Phases I-III for a comprehensive assessment of current conditions and recommended actions/projects. The request for the Comprehensive Stormwater Master Plan has been deferred due to limited funding in the last several years and is unlikely to be funded for a few more. | YES - updated/revised description provided at right, if applicable | Integrated into: Develop a Comprehensive Stormwater Master Plan.
14 | Complete Stormwater Master Plan Phase V | Phase V will complete the study of the Town’s stormwater system. Five of the Town’s twenty-two sub-basins will be studied as part of this project: Wayside, Square Meadow Brook, Reservoir #1 & #2 South, Reservoir #3 North, and Willow Brook drainage sub-basins. |  |  |  | 400000 | Capital budget | DPW | Long | 25.8 |  | Delayed | Rather than Phase IV and V, there is a request for a Comprehensive Stormwater Master Plan that would incorporate Phases IV and V but also revisit Phases I-III for a comprehensive assessment of current conditions and recommended actions/projects. The request for the Comprehensive Stormwater Master Plan has been deferred due to limited funding in the last several years and is unlikely to be funded for a few more. | YES - updated/revised description provided at right, if applicable | Integrated into: Develop a Comprehensive Stormwater Master Plan.
15 | Develop green infrastructure marketing/education program to business community | Develop green infrastructure marketing/education program to business community. Could additionally leverage technical assistance via a consultant. Note: the NPDES MS4 permit will require the Town to provide public education to businesses, institutions, commercial facilities, and developers. |  |  |  | Working Group/Town staff | Working Group/Town staff | N/A | Working Group/Town staff | 25.8 |  | In Progress | Ongoing. Need support and funding. | YES - updated/revised description provided at right, if applicable | Carried directly into HMP Update: "Develop and implement a municipal program to promote the use of green infrastructure to the business community."
42 | PILOT NEIGHBORHOOD PROJECT: Acquisition and Relocation or flood protection of private properties with repetitive loss in Walnut Street neighborhood | Identify, acquire, and/or relocate flood-prone buildings so that they are out of the floodplain. Place restrictions on purchased land in floodplain to prevent future development. Identify and protect existing flood-prone buildings by floodproofing, elevation, or minor structural projects. Assume 171, 175, & 179 Walnut Street. Potentially more properties on eastern side of Walnut Street. |  |  |  | $1.3M | FEMA funding; Administrative | MHMP Working Group | Long | 20.2 |  | In Progress | In August 2021, the City of Framingham received a $269,030 Municipal Vulnerability Preparedness (MVP) Action Grant from the Baker-Polito Administration to support the project. In February 2020, the City received a $206,850 MVP Action Grant from the Baker-Polito Administration to support the project. | YES - updated/revised description provided at right, if applicable | Integrated into: "Protect or acquire private property impacted by flooding in repetitive loss neighborhoods".
OTHER MITIGATION MEASURES FROM 2017 LIST (BUT NOT PRIORITIES, AND NOT PART OF 2017 ACTION PLAN):
16 | Construct Walnut Street Sewer Pump Station | Measure to replace an existing pump station with a new pump station. Following an assessment of alternative solutions, it was determined that rehabilitation of the existing Worcester Road Pump Station was the most cost effective option. |  |  |  | N/A | MassDEP State Revolving Loan Program | DPW | Short | 25.4 |  | In Progress | The Walnut St Pump Station construction was to replace the Worcester Rd pump station. After analysis on constructing the Walnut St Pump Station it was determined the more cost effective approach was to rehab the existing Worcester Rd Pump Station in its existing location. The design is complete and that project is scheduled to be put out to bid for construction this year. More details on the project can be found here: https://www.framinghamma.gov/3413/Worcester-Road-Sewer-Pump-Station-Rehabi. | YES - updated/revised description provided at right, if applicable | Integrated into: "Complete rehabilitation of the Worcester Road Sewer Pump Station."
17 | Nobscot Fire Station Area Drainage Improvements | N/A |  |  |  | N/A | DPW | DPW | N/A | 25.4 |  | In Progress | Drainage improvements are in the process of being implemented as part of local development of the Nobscott Plaza. DPW also previously made improvements to stormwater infrastructure for Fire Station #7. | YES - updated/revised description provided at right, if applicable | Integrated into: "Implement draingage improvements to support transportation networks and associated properties."
18 | Web-based Public Portal for Stream Gauge Data | N/A |  |  |  | N/A | DPW | DPW | N/A | 25 |  | In Progress | See Action 4. DPW replaced four existing stream gauges in July 2018 with upgraded technology with web portal. | YES - updated/revised description provided at right, if applicable | Integrated into: "Install additional stream gauges and web-based public portal for stream gauge data."
19 | School Street bridge replacement | N/A |  |  |  | N/A | DPW | DPW | Medium | 24.6 |  | Delayed | Highlighted as part of a recent visit by U.S. House Assistant Speaker to highlight need for infrastructure funding. Framingham anticipating pursuing grant funding for this measure. Currently highest priority bridge replacement project. | YES - updated/revised description provided at right, if applicable | Integrated into: "Replace the School Street, Taralli Terrace, and Second Street Bridges."
20 | CRS Program Assessment | FEMA Community Rating System (CRS) is a voluntary incentive program that recognizes and encourages community floodplain management practices that exceed the minimum requirements of the National Flood Insurance Program (NFIP). |  |  |  | N/A | Working Group / City Staff | DPW | N/A | 24.4 |  | Delayed | The City is not currently listed as a particiating community in the CRS Program. | NO - explanation provided at left | Removed: lacking capacity to implement.
21 | Fountain Street Drainage Improvement | Implementation of drainage improvements at Fountain Street. |  |  |  | Total Intersection Improvement Costs: $3.9 million | DPW | DPW | Medium | 24.2 |  | Partially Completed / In Progress | Comprhensive improvements to the Fountain Street intersection are underway. This project includes drainage improvements that will benefit the water quality of Farm Pond. Easement acquisitions will take place this year, along with utility pole installation and overhead wire transfers. Funding sources for the final design and construction are being reviewed. | YES - updated/revised description provided at right, if applicable | Integrated into: "Implement draingage improvements to support transportation networks and associated properties. "
22 | Expand rain barrel program | Rain barrel program to provide discounted rain barrels to residents. |  |  |  | N/A | DPW | DPW | N/A | 24 |  | Delayed | Rain barrel program was cancelled during the pandemic. | YES - updated/revised description provided at right, if applicable | Intregated into: "Reimplement residential rain barrel program."
23 | Taralli Terrace Bridge replacement | Replacement of Taralli Terrace Bridge |  |  |  | Evaluation Cost for Taralli & Second Street Bridges: $100,000 | DPW | DPW | Long | 24 |  | In Progress | Evaluation of bridge on CIP for 2025 request. | YES - updated/revised description provided at right, if applicable | Integrated into: "Replace the School Street, Taralli Terrace, and Second Street Bridges."
24 | Second Street Bridge replacement | Replacement of Second Street Bridge |  |  |  | Evaluation Cost for Taralli & Second Street Bridges: $100,000 | DPW | DPW | Long | 24 |  | In Progress | Evaluation of bridge on CIP for 2025 request. | YES - updated/revised description provided at right, if applicable | Integrated into: "Replace the School Street, Taralli Terrace, and Second Street Bridges."
25 | Replace Farm Pond outfall | See Action 21. |  |  |  | See Action 21 | DPW | DPW | Medium | 23.8 |  | Delayed | To be completed as part of Item 21: Fountain Street Drainage Improvement. Planned to be funded in FY 2024. | YES - updated/revised description provided at right, if applicable | Integrated into: "Implement draingage improvements to support transportation networks and associated properties. "
26 | Culvert retrofit at Fuller School pedestrian path | Culvert retrofit to support path behind Fuller Middle School coming from Fraser Road. |  |  |  | N/A | N/A | DPW | Medium | 23.8 |  | Delayed | No updates on this specific action. Stormwater improvements related to new school have significantly reduced impervious surface area in the neighborhood (a reduction of about 1/4 impervious surface). Several culvert retorfits included under this work and areas behind Fuller School with underground chambers for stormwater management. Drainage improvements at the site may have alleviated the issues here. Challenges with sewer infrastructure may complicatethis project. Culvert and trench need to be evaluated for retrofit. | YES - updated/revised description provided at right, if applicable | Integrated into: "Retrofit, update, or replace undersized and unsafe culverts."
27 | Emergency generators for general store | N/A |  |  |  | N/A | N/A | N/A | N/A | 23.6 |  | Cancelled | No information at this time. Any progress that has been made has been community-driven as there is no municpal program to supprot this currently. | NO - explanation provided at left | Removed; organized within community, unclear role for municipality.
28 | Woodfield Playground infiltration system | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 23.2 |  | Delayed | May be indirectly supported by prospective restoration work done as part of Rail Trail acquisition. Unclear as to specific measure identified here. | YES - updated/revised description provided at right, if applicable | Covered by: "Acquire the CSX Corridor and implement next steps to develop the Bruce Freeman Rail Trail."
29 | Install green infrastructure in the vicinity of Butterworth Park | N/A |  |  |  | N/A | N/A | N/A | N/A | 23 |  | Delayed | No action has been taken on this measure. | YES - updated/revised description provided at right, if applicable | Integrated into: "Deploy green infratructure on municipal properties to improve stormwater management and reduce heat island impacts."
30 | Develop hazard mitigation incentive program | N/A |  |  |  | N/A | N/A | N/A | N/A | 23 |  | Delayed | No action has been taken on this measure. | YES - updated/revised description provided at right, if applicable | Integrated into: "Explore the development of a Hazard Mitigation Incentive Program."
31 | Constructed wetlands or wetlands restoration project | N/A |  |  |  | $200k | DPW/ARPA | DPW | N/A | 23 |  | In Progress | City is pursuing conditions assessment and potential wetlands restoration to improve water quality at a Lake Waushakum outfall. | YES - updated/revised description provided at right, if applicable | Integrated into: "Protect and restore wetland areas, including around Lake Waushakum."
32 | Flood Protection of private property with flood loss in Hemenway neighborhood | N/A |  |  |  | N/A | DPW | DPW | N/A | 22.8 |  | Delayed | Would be supproted by MVP action regarding the removal of the Landham Pond Dam which is tied to acqusition of rail line. | YES - updated/revised description provided at right, if applicable | Integrated into: "Protect or acquire private property impacted by flooding in repetitive loss neighborhoods."
33 | Flood Protection of private property with repetitive loss in Auburn Street neighborhood | N/A |  |  |  | N/A | DPW | DPW | N/A | 22.8 |  | In Progress | In order to mitigate this problem, the City decided to install two backflow preventers, a component of which is a “duckbill” style check valve. 3 out of 4 duckbill devices were allowed for installation. | YES - updated/revised description provided at right, if applicable | Integrated into: "Protect or acquire private property impacted by flooding in repetitive loss neighborhoods."
34 | Flood Protection of private property with repetitive loss in Circle Drive neighborhood | N/A |  |  |  | N/A | DPW | DPW | N/A | 22.8 |  | Delayed | No action is currently planned for this neighborhood. | YES - updated/revised description provided at right, if applicable | Integrated into: "Protect or acquire private property impacted by flooding in repetitive loss neighborhoods."
35 | Flood Protection of private property with repetitive loss in Prescott St neighborhood | N/A |  |  |  | N/A | DPW | DPW | N/A | 22.8 |  | Delayed | No action is currently planned for this neighborhood. | YES - updated/revised description provided at right, if applicable | Integrated into: "Protect or acquire private property impacted by flooding in repetitive loss neighborhoods."
36 | Develop and implement a residential rain garden program. | Develop and implement a residential rain garden program. |  |  |  | N/A | N/A | N/A | N/A | 22.6 |  | Delayed | No update currently, however, Framingham is participating in an MVP Project titled the Sudbury-Assabet-Concord Natural Climate Solutions Grant that may support nature-based solutions. | YES - updated/revised description provided at right, if applicable | Removed; City will be pursuing opportunities through MVP Sudbury-Assabet-Concord Natural Climate Solutions Grant.
37 | Charlotte Dunning School green infrastructure | N/A |  |  |  | 500000 | Schools (Capital) | Schools | 2016/2017 | 22.6 |  | Completed | As part of parking lot project, the Schools added a new drainage swale and catchbasin. | NO - explanation provided at left | Completed.
38 | Edmands Road culvert upgrade | This project is being addressed through Nobscott Intersection Improvements. |  |  |  | $3.4 million (Grant) | Massworks Grant | DPW | Short | 22.4 |  | Partially Completed / In Progress | An emergency repair to the culvert was completed in 2021. Nobscott Intersection Project currently in progress with construction underway as of March. More information avialable here: https://www.framinghamma.gov/2314/Nobscot-Intersection-Improvements. | YES - updated/revised description provided at right, if applicable | Integrated into: " Retrofit, update, or replace undersized and unsafe culverts."
39 | Install beaver deceivers near pedestrian bridge near high school | Check with Schools (Schools were improving drainage infrastructure) |  |  |  | N/A | N/A | N/A | N/A | 21.4 |  | Delayed | No action. | NO - explanation provided at left | Removed; a more comprehesnive exploration of solutions will be made through the development of a Beaver Management Plan.
40 | Flood Protection of Town Buildings | N/A |  |  |  | N/A | N/A | N/A | N/A | 21 |  | Partially Completed / In Progress | Flood proofing has been done for facilities such as the Callahan Senior Center. Stormwater improvements have been implemented at Fire Station #7 but the facility is still vulnerable to flooding neccessitating the use of sandbags near the entrance to the basement. Improvements to Station #7 have improved the situation, but the site is still vulnerable to severe storms. McCarthy experiences flooding from groundwater, school has several sump pumps and perimeter drainage system. Worcester Road Pumping Station rehabilitation will provide additional resiliency. | NO - explanation provided at left | Removed; progress has been made on municipal facilities. Concerns about Station #7 have been included in "Implement draingage improvements to support transportation networks and associated properties. "
41 | Acquisition and Relocation or flood protection of private properties with repetitive loss in Beaver Dam Brook neighborhood | Acquisition and Relocation or flood protection of private properties with repetitive loss in Beaver Dam Brook neighborhood. |  |  |  | See New Measure to Acquire 103 Guild Street Property | See New Measure to Acquire 103 Guild Street Property | See New Measure to Acquire 103 Guild Street Property | See New Measure to Acquire 103 Guild Street Property | 20.6 |  | Partially Completed / In Progress | See New Measure to Acquire 103 Guild Street Property. Also, 350 Irving Street project will result in dredging in Beaver Dam Brook that will alleviate flooding. City is pursuing opportunities through this to restore the floodplain. | YES - updated/revised description provided at right, if applicable | Integrated into: "Protect or acquire private property impacted by flooding in repetitive loss neighborhoods."
43 | Rehabilitate flood control berm at Callahan Senior Center | N/A |  |  |  | N/A | N/A | DPW | N/A | 20 |  | Completed | Related work has been done in the Callahan Senior Center basement as of 2019 to mitigate flooding. The floor has been raised more than a foot to mitigate flooding issues. | NO - explanation provided at left | Removed: A flooding mitigation project in the basement of the Callahan Senior Center has been completed.
44 | Acquisition and Relocation or flood protection of private properties with repetitive loss in Auburn Street neighborhood | N/A |  |  |  | N/A | N/A | CPD | N/A | 19.8 |  | Delayed | N/A; specific properties unclear. | YES - updated/revised description provided at right, if applicable | Integrated into: "Protect or acquire private property impacted by flooding in repetitive loss neighborhoods."
45 | Relocation of Town Buildings out of floodplain | N/A |  |  |  | N/A | N/A | N/A | N/A | 17.8 |  | Cancelled | Not feasible to implement, City will not pursue due to cost and space constraints. | NO - explanation provided at left | Cancelled.

## Previous Mitigation Actions WIP (hidden)
Action # | Action Title | Action Description | Mitigation Goal | Mitigation Category | Hazard(s) Addressed | Estimated Cost | Potential Funding Source | Lead Department | Implementation Schedule | Priority Score | Priority | Current Status | Status Description / Explanation | Keep for Updated Plan? | Updated Action Title/Description (if applicable)
1 | Evaluate and enhance current bylaws and regulations regarding floodplain development | Review zoning bylaw, wetlands bylaw, building code, and health & safety regulations in order to ensure consistency across the regulations and most modern information is included. Could additionally leverage technical assistance via a consultant. Review Planning & Wetlands bylaws in regards to allowable development in floodplains. Currently, development is not prohibited, but mitigation is needed. Bylaw revisions need to be approved at Town Meeting. This is one of the activities to get credit for the CRS program. | TBD |  |  | Working Group/Town staff | Working Group/Town staff | N/A | Working Group/Town staff | 28.4 |  | Delayed | Due to limited planning staff this has not progressed, however, now that we have a new Planning Director, this is on the list of projects for the next few years. | YES - updated/revised description provided at right, if applicable
2 | Purchase & install 4 automated weather stations and Install Web-based Public Portal for Stream Gauge Data | Purchase and install 4 automated weather stations throughout Town, with web-based access. Weather stations will assist DPW personnel with assessing storms to improve response to extreme precipitation, high winds, and winter storms. They will also assist Police & Fire with emergency response for storm events. The DPW Highway Department use pavement sensors to evaluate the temperature of pavement during cold weather. This data enables the Highway Department to identify roads for pretreatment which reduces roadway icing and other hazards associated with winter storms. | TBD |  |  | 10000 | Operating budget; FEMA funding | DPW | Short | 27.6 |  | In Progress | We should consider the use of this term- 'Delayed'. We would like to eventually have this capability but currently do not have funding. | YES - updated/revised description provided at right, if applicable
3 | Integrate flood storage review into open space plan | The Town's current Open Space & Recreation Plan creates a priority list of open space parcels for the Town to consider protecting from future development. Integrating flood storage capacity as a criterion in this analysis would reflect properties that would be prime candidates for increasing flood storage and mitigate flooding impacts. | TBD |  |  | Working Group/Town staff | Working Group/Town staff | N/A | Working Group/Town staff | 27.4 |  | In Progress | This is mentioned in the 2020 OSRP but the OSRP has not been finalized at this time due to staffing constraints and high staff turnover. | YES - updated/revised description provided at right, if applicable
4 | Install additional stream gauges and Web-based Public Portal for Stream Gauge Data | Install additional automated stream gauges (surface water level sensors and communications equipment) at high risk areas. Angelica Drive (Angelica Brook) Bates Rd (Beaver Dam Brook) | TBD |  |  | $15,000-$30,000/each | Capital budget; FEMA funding | DPW | Medium | 26.8 |  | In Progress | Ongoing as funding allows. We recently acquired new stream gauges and are in the process of installing them. The selected locations have been revised. Keep on the list because we would like to add more as funding allows. DPW replaced four existing stream gauges in July 2018 with upgraded technology with web portal. Transparency forthcoming. | YES - updated/revised description provided at right, if applicable
5 | Enhance current bylaws and regulations to prevent future development in the floodplain | Review Planning & Wetlands bylaws in regards to allowable development in floodplains. Currently, development is not prohibited, but mitigation is needed. Bylaw revisions need to be approved at Town Meeting. This is one of the activities to get credit for the CRS program. | TBD |  |  | Working Group/Town staff | Working Group/Town staff | N/A | Working Group/Town staff | 26.8 |  | In Progress | Due to limited planning staff this has not progressed, however, now that we have a new Planning Director, this is on the list of projects for the next few years. | YES - updated/revised description provided at right, if applicable
6 | Install additional pavement sensors | The DPW Highway Department use pavement sensors to evaluate the temperature of pavement during cold weather. This data enables the Highway Department to identify roads for pretreatment which reduces roadway icing and other hazards associated with winter storms. | TBD |  |  | 20000 | Operating budget; FEMA funding | DPW | Short | 26.4 |  | In Progress | DPW Highway installed a couple sensors, however, were difficult to maintain, and expensive. No current funding available. Low priority. | YES - updated/revised description provided at right, if applicable
7 | Develop stormwater bylaw & regulations | Develop bylaws for stormwater management for new and re- development within Town. | TBD |  |  | Working Group/Town staff | Working Group/Town staff | N/A | Working Group/Town staff | 26.4 |  | Completed | COMPLETE - **Current updates comply with MS4 but might need further improvemets to reduce current flooding problems | NO - explanation provided at left
8 | Develop green infrastructure bylaw & regulations | Develop bylaws for green infrastructure for new and re- development within Town. Could additionally leverage technical assistance via a consultant. Note: the NPDES MS4 permit will require the Town to assess local regulations regarding green infrastructure by 2021. |  |  |  | Working Group/Town staff | Working Group/Town staff | N/A | Working Group/Town staff | 26.2 |  | Completed | COMPLETE – Current regulations were reviewed by VHB and MassAudubon and subsequent bylaws have been updated (Subdivision Rules and Regs, Zoning Bylaw, etc.) | NO - explanation provided at left
9 | Emergency generators for traffic signals | Power can be lost during winter storm events or high winds, including power used for traffic signals. For example, during a 2013 storm event, power was lost at a major intersection's traffic signal for 6 days. Police details were required, pulling limited emergency personnel from other weather-related emergencies. Loss of power to traffic signals compounds hazardous travel conditions. Emergency, back-up generators for traffic signals will help facilitate traffic flow and mitigate hazardous conditions. |  |  |  | 10000 | Operating budget; FEMA funding | DPW/Police | Medium | 26.2 |  | Delayed | Potentially bundle these into one capital project for FY20 or FY21. KR to discuss with DPW. | YES - updated/revised description provided at right, if applicable
10 | Conduct a Climate Change Vulnerability Assessment | The Climate Change Vulnerability Assessment would help the Town understand how we are vulnerable or resilient to potential climate change in terms of impacts on people, infrastructure, public health, and the economy. It would serve as the technical reference for identifying and planning mitigation projects. The Town would also use it to revise Town regulations for private development to improve resiliency. |  |  |  | $75,000-$100,000 | FEMA funding | C&ED/DPW | Long | 26 |  | Completed | In progress. City was awarded funding under the MVP Program in 2018. Fuss & O’Neill conduct a climate change analysis. City to begin Climate Action Planning with the central goal of establishing long-term strategies and actions to reduce local greenhouse gas emissions. The focus on the plan will be less on natural hazards and more so in mitigating the City's contribution to greenhouse gas emissions and identifying opportunities to advance the long-term social, economic, and enviornmental health of the community. | NO - explanation provided at left
11 | Culvert replacement at CSX crossing of Hop Brook | Feasibility of a culvert replacement will be analyzed as part of the Landham Pond Dam Removal project. The culvert will be rehabilitated or replaced to increase capacity and meet stream crossing standards. Would require site control/CSX corridor acquisition. |  |  |  | $1.5M | FEMA funding | DPW | Long | 26 |  | In Progress | DPW secured $150K DER grant funding to study the replacement of the City-owned Colonial Drive culvert which is the last culvert downstream of the CSX culverts and will need to be upgraded before the CSX culverts can be upgraded. Anticipated June 2019 | YES - updated/revised description provided at right, if applicable
12 | Prepare, adopt, implement, and update a comprehensive flood hazard mitigation plan | Use standard planning process (similar to the MHMP process) to develop plan. Plan would need to be approved by Board of Selectmen. Updates would be required every 5 years. This is a minimum requirement for the CRS program for all repetitive loss communities. |  |  |  | 50000 | FEMA funding; Administrative | C&ED/DPW | Medium | 26 |  | Delayed | Due to limited planning staff this has not progressed, however, now that we have a new Planning Director, this is on the list of projects for the next few years. | YES - updated/revised description provided at right, if applicable
| Complete Comprehensive Stormwater Mater Plan | The Comprehensive Stormwater Master Plan will complete Phases IV and V of the City's study of the stromwater system. |  |  |  | 950000 | Capital Budget | DPW | Medium |  |  | Delayed | The request for the Comprehensive Stormwater Master Plan has been deferred due to limited funding in the last several years and is unlikely to be funded for a few more.
13 | Complete Stormwater Master Plan Phase IV | Phase IV will continue the study of the Town’s stormwater system. Five of the Town’s twenty-two sub-basins will be studied as part of this project: North and South Saxonville, Cherry Meadow Brook, Birch Meadow Brook and Baiting Brook drainage sub-basins. |  |  |  | 450000 | Capital budget | DPW | Medium | 25.8 |  | Delayed | Rather than Phase IV and V, there is a request for a Comprehensive Stormwater Master Plan that would incorporate Phases IV and V but also revisit Phases I-III for a comprehensive assessment of current conditions and recommended actions/projects. The request for the Comprehensive Stormwater Master Plan has been deferred due to limited funding in the last several years and is unlikely to be funded for a few more. | YES - updated/revised description provided at right, if applicable
14 | Complete Stormwater Master Plan Phase V | Phase V will complete the study of the Town’s stormwater system. Five of the Town’s twenty-two sub-basins will be studied as part of this project: Wayside, Square Meadow Brook, Reservoir #1 & #2 South, Reservoir #3 North, and Willow Brook drainage sub-basins. |  |  |  | 400000 | Capital budget | DPW | Long | 25.8 |  | Delayed | Rather than Phase IV and V, there is a request for a Comprehensive Stormwater Master Plan that would incorporate Phases IV and V but also revisit Phases I-III for a comprehensive assessment of current conditions and recommended actions/projects. The request for the Comprehensive Stormwater Master Plan has been deferred due to limited funding in the last several years and is unlikely to be funded for a few more. | YES - updated/revised description provided at right, if applicable
15 | Develop green infrastructure marketing/education program to business community | Develop green infrastructure marketing/education program to business community. Could additionally leverage technical assistance via a consultant. Note: the NPDES MS4 permit will require the Town to provide public education to businesses, institutions, commercial facilities, and developers. |  |  |  | Working Group/Town staff | Working Group/Town staff | N/A | Working Group/Town staff | 25.8 |  | In Progress | Ongoing. Need support and funding. | YES - updated/revised description provided at right, if applicable
42 | PILOT NEIGHBORHOOD PROJECT: Acquisition and Relocation or flood protection of private properties with repetitive loss in Walnut Street neighborhood | Identify, acquire, and/or relocate flood-prone buildings so that they are out of the floodplain. Place restrictions on purchased land in floodplain to prevent future development. Identify and protect existing flood-prone buildings by floodproofing, elevation, or minor structural projects. Assume 171, 175, & 179 Walnut Street. Potentially more properties on eastern side of Walnut Street. |  |  |  | $1.3M | FEMA funding; Administrative | MHMP Working Group | Long | 20.2 |  | In Progress | In August 2021, the City of Framingham received a $269,030 Municipal Vulnerability Preparedness (MVP) Action Grant from the Baker-Polito Administration to support the project. In February 2020, the City received a $206,850 MVP Action Grant from the Baker-Polito Administration to support the project. | YES - updated/revised description provided at right, if applicable
OTHER MITIGATION MEASURES FROM 2017 LIST (BUT NOT PRIORITIES, AND NOT PART OF 2017 ACTION PLAN):
16 | Construct Walnut Street Sewer Pump Station | Measure to replace an existing pump station with a new pump station. Following an assessment of alternative solutions, it was determined that rehabilitation of the existing Worcester Road Pump Station was the most cost effective option. |  |  |  | N/A | MassDEP State Revolving Loan Program | DPW | Short | 25.4 |  | In Progress | The Walnut St Pump Station construction was to replace the Worcester Rd pump station. After analysis on constructing the Walnut St Pump Station it was determined the more cost effective approach was to rehab the existing Worcester Rd Pump Station in its existing location. The design is complete and that project is scheduled to be put out to bid for construction this year. More details on the project can be found here: https://www.framinghamma.gov/3413/Worcester-Road-Sewer-Pump-Station-Rehabi. | YES - updated/revised description provided at right, if applicable | Worcester Road Pump Station Rehabilitation
| Implement Drainage Improvements | Nobscott Fire Station Area, Fountain Street Area | [10 empty] | Fountain Street - Comprhensive improvements to the Fountain Street intersection are underway. This project includes drainage improvements that will benefit the water quality of Farm Pond. Easement acquisitions will take place this year, along with utility pole installation and overhead wire transfers. Funding sources for the final design and construction are being reviewed. Nobscott Area - Drainage improvements are in the process of being implemented as part of local development of the Nobscott Plaza. DPW also previously made improvements to stormwater infrastructure for Fire Station #7.
17 | Nobscot Fire Station Area Drainage Improvements | N/A |  |  |  | N/A | DPW | DPW | N/A | 25.4 |  | In Progress | Drainage improvements are in the process of being implemented as part of local development of the Nobscott Plaza. DPW also previously made improvements to stormwater infrastructure for Fire Station #7. | YES - updated/revised description provided at right, if applicable
18 | Web-based Public Portal for Stream Gauge Data | N/A |  |  |  | N/A | DPW | DPW | N/A | 25 |  | In Progress | See Action 4. DPW replaced four existing stream gauges in July 2018 with upgraded technology with web portal. | YES - updated/revised description provided at right, if applicable
| Replace School Street, Taralli Terrace, and Second Street Bridges | Replacement of bridges. |  |  |  |  | DPW | DPW | Long |  |  |  | Highlighted as part of a recent visit by U.S. House Assistant Speaker to highlight need for infrastructure funding. Framingham anticipating pursuing grant funding for this measure. Currently highest priority bridge replacement project. Taralli Street - Evaluation of bridge on CIP for 2025 request. Second Street - Evaluation of bridge on CIP for 2025 request.
19 | School Street bridge replacement | N/A |  |  |  | N/A | DPW | DPW | Medium | 24.6 |  | Delayed | Highlighted as part of a recent visit by U.S. House Assistant Speaker to highlight need for infrastructure funding. Framingham anticipating pursuing grant funding for this measure. Currently highest priority bridge replacement project. | YES - updated/revised description provided at right, if applicable
20 | CRS Program Assessment | FEMA Community Rating System (CRS) is a voluntary incentive program that recognizes and encourages community floodplain management practices that exceed the minimum requirements of the National Flood Insurance Program (NFIP). |  |  |  | N/A | Working Group / City Staff | DPW | N/A | 24.4 |  | Delayed | The City is not currently listed as a particiating community in the CRS Program. | YES - updated/revised description provided at right, if applicable
21 | Fountain Street Drainage Improvement | Implementation of drainage improvements at Fountain Street. |  |  |  | Total Intersection Improvement Costs: $3.9 million | DPW | DPW | Medium | 24.2 |  | Partially Completed / In Progress | Comprhensive improvements to the Fountain Street intersection are underway. This project includes drainage improvements that will benefit the water quality of Farm Pond. Easement acquisitions will take place this year, along with utility pole installation and overhead wire transfers. Funding sources for the final design and construction are being reviewed. | YES - updated/revised description provided at right, if applicable
22 | Reimplement Rain Barrel Program | Rain barrel program to provide discounted rain barrels to residents. |  |  |  | N/A | DPW | DPW | N/A | 24 |  | Delayed | Rain barrel program was cancelled during the pandemic. | YES - updated/revised description provided at right, if applicable | Restore rain barrel program.
23 | Taralli Terrace Bridge replacement | Replacement of Taralli Terrace Bridge |  |  |  | Evaluation Cost for Taralli & Second Street Bridges: $100,000 | DPW | DPW | Long | 24 |  | In Progress | Evaluation of bridge on CIP for 2025 request. | YES - updated/revised description provided at right, if applicable
24 | Second Street Bridge replacement | Replacement of Second Street Bridge |  |  |  | Evaluation Cost for Taralli & Second Street Bridges: $100,000 | DPW | DPW | Long | 24 |  | In Progress | Evaluation of bridge on CIP for 2025 request. | YES - updated/revised description provided at right, if applicable
25 | Replace Farm Pond Outfall | See Action 21. |  |  |  | See Action 21 | DPW | DPW | Medium | 23.8 |  | Delayed | To be completed as part of Item 21: Fountain Street Drainage Improvement. Planned to be funded in FY 2024. | YES - updated/revised description provided at right, if applicable
| Retrofit and Update Culverts to Handle Increase Volumes of Stormwater | Fuller School pedestrian path culvert, Edmands Road culvert upgrade, and CSX Hop Brook Culvert. Feasibility of a culvert replacement will be analyzed as part of the Landham Pond Dam Removal project. The culvert will be rehabilitated or replaced to increase capacity and meet stream crossing standards. Would require site control/CSX corridor acquisition. | [10 empty] | Fuller School pedestrian path - "No updates on this specific action. Stormwater improvements related to new school have significantly reduced impervious surface area in the neighborhood (a reduction of about 1/4 impervious surface). Several culvert retorfits included under this work and areas behind Fuller School with underground chambers for stormwater management. Drainage improvements at the site may have alleviated the issues here. Challenges with sewer infrastructure may complicatethis project. Culvert and trench need to be evaluated for retrofit. " An emergency repair to the culvert was completed in 2021. Nobscott Intersection Project currently in progress with construction underway as of March. More information avialable here: https://www.framinghamma.gov/2314/Nobscot-Intersection-Improvements. Hop Brook - DPW secured $150K DER grant funding to study the replacement of the City-owned Colonial Drive culvert which is the last culvert downstream of the CSX culverts and will need to be upgraded before the CSX culverts can be upgraded. Anticipated June 2019
26 | Culvert retrofit at Fuller School pedestrian path | Culvert retrofit to support path behind Fuller Middle School coming from Fraser Road. |  |  |  | N/A | N/A | DPW | Medium | 23.8 |  | Delayed | No updates on this specific action. Stormwater improvements related to new school have significantly reduced impervious surface area in the neighborhood (a reduction of about 1/4 impervious surface). Several culvert retorfits included under this work and areas behind Fuller School with underground chambers for stormwater management. Drainage improvements at the site may have alleviated the issues here. Challenges with sewer infrastructure may complicatethis project. Culvert and trench need to be evaluated for retrofit. | YES - updated/revised description provided at right, if applicable
27 | Emergency generators for general store | N/A |  |  |  | N/A | N/A | N/A | N/A | 23.6 |  | Cancelled | No information at this time. Any progress that has been made has been community-driven as there is no municpal program to supprot this currently. | NO - explanation provided at left
28 | Woodfield Playground infiltration system | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 23.2 |  | Delayed | May be indirectly supported by prospective restoration work done as part of Rail Trail acquisition. Unclear as to specific measure identified here. | NO - explanation provided at left | Unclear as to what measure this is in reference to.
29 | Install green infrastructure in the vicinity of Butterworth Park | N/A |  |  |  | N/A | N/A | N/A | N/A | 23 |  | Delayed | No action has been taken on this measure. | YES - updated/revised description provided at right, if applicable
30 | Develop hazard mitigation incentive program | N/A |  |  |  | N/A | N/A | N/A | N/A | 23 |  | Delayed | No action has been taken on this measure. | YES - updated/revised description provided at right, if applicable | No action has been taken and next steps are unclear so this action will be removed.
31 | Constructed wetlands or wetlands restoration project | N/A |  |  |  | $200k | DPW/ARPA | DPW | N/A | 23 |  | In Progress | City is pursuing conditions assessment and potential wetlands restoration to improve water quality at a Lake Waushakum outfall. | YES - updated/revised description provided at right, if applicable
| Flood Protection or Acquisition of Private Property in Repetitive Loss Neighborhoods | Flood protection of neighborhoods including proprties on Hemenway and Auburn Streets. Acquire properties along the Sudbury River for flood storage. Acquisition and Relocation or flood protection of private properties with repetitive loss in Walnut Street neighborhood |  |  |  | $$$ | FEMA funding; Administrative |  | 2035-12-01 |  |  | In Progress | Hemenway - Efforts will be supported by an MVP Action Grant regarding removal of Landham Pond Dam which is tied to acquisition of the rail trail property. Auburn - In order to mitigate this problem, the City decided to install two backflow preventers, a component of which is a “duckbill” style check valve. 3 out of 4 duckbill devices were allowed for installation. Beaver Dam Brook - Acquisition of 103 Guld Street will support will help alleviate flooding issues in this neighborhood. Walnut Street - Identify, acquire, and/or relocate flood-prone buildings so that they are out of the floodplain. Place restrictions on purchased land in floodplain to prevent future development. Identify and protect existing flood-prone buildings by floodproofing, elevation, or minor structural projects. Assume 171, 175, & 179 Walnut Street. Potentially more properties on eastern side of Walnut Street. "In August 2021, the City of Framingham received a $269,030 Municipal Vulnerability Preparedness (MVP) Action Grant from the Baker-Polito Administration to support the project. In February 2020, the City received a $206,850 MVP Action Grant from the Baker-Polito Administration to support the project. " | YES - updated/revised description provided at right, if applicable
32 | Flood Protection of private property with flood loss in Hemenway neighborhood | N/A |  |  |  | N/A | DPW | DPW | N/A | 22.8 |  | Delayed |  | YES - updated/revised description provided at right, if applicable
33 | Flood Protection of private property with repetitive loss in Auburn Street neighborhood | N/A |  |  |  | N/A | DPW | DPW | N/A | 22.8 |  | In Progress | In order to mitigate this problem, the City decided to install two backflow preventers, a component of which is a “duckbill” style check valve. 3 out of 4 duckbill devices were allowed for installation. | YES - updated/revised description provided at right, if applicable
34 | Flood Protection of private property with repetitive loss in Circle Drive neighborhood | N/A |  |  |  | N/A | DPW | DPW | N/A | 22.8 |  | Delayed | No action is currently planned for this neighborhood. | YES - updated/revised description provided at right, if applicable
35 | Flood Protection of private property with repetitive loss in Prescott St neighborhood | N/A |  |  |  | N/A | DPW | DPW | N/A | 22.8 |  | Delayed | No action is currently planned for this neighborhood. | YES - updated/revised description provided at right, if applicable
36 | Develop and implement a residential rain garden program. | Develop and implement a residential rain garden program. |  |  |  | N/A | N/A | N/A | N/A | 22.6 |  | Delayed | No update currently, however, Framingham is participating in an MVP Project titled the Sudbury-Assabet-Concord Natural Climate Solutions Grant that may support nature-based solutions. | YES - updated/revised description provided at right, if applicable
| Implement Green Infrastructure to increase resilience to local flooding. | Butterworth Park | [10 empty] | No update currently, however, Framingham is participating in an MVP Project titled the Sudbury-Assabet-Concord Natural Climate Solutions Grant that may support nature-based solutions. | YES - updated/revised description provided at right, if applicable
37 | Charlotte Dunning School green infrastructure | N/A |  |  |  | 500000 | Schools (Capital) | Schools | 2016/2017 | 22.6 |  | Completed | As part of parking lot project, the Schools added a new drainage swale and catchbasin. | NO - explanation provided at left
38 | Edmands Road culvert upgrade | This project is being addressed through Nobscott Intersection Improvements. |  |  |  | $3.4 million (Grant) | Massworks Grant | DPW | Short | 22.4 |  | Partially Completed / In Progress | An emergency repair to the culvert was completed in 2021. Nobscott Intersection Project currently in progress with construction underway as of March. More information avialable here: https://www.framinghamma.gov/2314/Nobscot-Intersection-Improvements. | YES - updated/revised description provided at right, if applicable
39 | Install beaver deceivers near pedestrian bridge near high school | Check with Schools (Schools were improving drainage infrastructure) |  |  |  | N/A | N/A | N/A | N/A | 21.4 |  | Delayed | No action. | YES - updated/revised description provided at right, if applicable | Need to develop plan on handling beavers more comprehensively, so removing.
40 | Flood Protection of Town Buildings | N/A |  |  |  | N/A | N/A | N/A | N/A | 21 |  | Partially Completed / In Progress | Flood proofing has been done for facilities such as the Callahan Senior Center. Stormwater improvements have been implemented at Fire Station #7 but the facility is still vulnerable to flooding neccessitating the use of sandbags near the entrance to the basement. Improvements to Station #7 have improved the situation, but the site is still vulnerable to severe storms. McCarthy experiences flooding from groundwater, school has several sump pumps and perimeter drainage system. Worcester Road Pumping Station rehabilitation will provide additional resiliency. Related work has been done in the Callahan Senior Center basement as of 2019 to mitigate flooding. The floor has been raised more than a foot to mitigate flooding issues. | YES - updated/revised description provided at right, if applicable | Already in MVP priorities
41 | Acquisition and Relocation or flood protection of private properties with repetitive loss in Beaver Dam Brook neighborhood | Acquisition and Relocation or flood protection of private properties with repetitive loss in Beaver Dam Brook neighborhood. |  |  |  | See New Measure to Acquire 103 Guild Street Property | See New Measure to Acquire 103 Guild Street Property | See New Measure to Acquire 103 Guild Street Property | See New Measure to Acquire 103 Guild Street Property | 20.6 |  | Partially Completed / In Progress | See New Measure to Acquire 103 Guild Street Property. Also, 350 Irving Street project will result in dredging in Beaver Dam Brook that will alleviate flooding. City is pursuing opportunities through this to restore the floodplain. | YES - updated/revised description provided at right, if applicable
43 | Rehabilitate flood control berm at Callahan Senior Center | N/A |  |  |  | N/A | N/A | DPW | N/A | 20 |  | Completed | Related work has been done in the Callahan Senior Center basement as of 2019 to mitigate flooding. The floor has been raised more than a foot to mitigate flooding issues. | YES - updated/revised description provided at right, if applicable
44 | Acquisition and Relocation or flood protection of private properties with repetitive loss in Auburn Street neighborhood | N/A |  |  |  | N/A | N/A | CPD | N/A | 19.8 |  | Delayed | N/A; specific properties unclear. | YES - updated/revised description provided at right, if applicable
45 | Relocation of Town Buildings out of floodplain | N/A |  |  |  | N/A | N/A | N/A | N/A | 17.8 |  | Cancelled | Not feasible to implement, City will not pursue due to cost and space constraints. | NO - explanation provided at left

## MVP Recommendations
List | MVP Recommendation | Current Status | Current Status Description/Explanation | Notes / Comments (Provide feedback as to whether will be moving forward or not)
Highest Priority
1 | Conduct a field inventory of culverts and bridges to rank and prioritize projects for increased flooding resiliency and storm-hardening, followed by design and implementation of priority resizing or replacement projects. Green infrastructure, Low-Impact Design, and other nature-based solutions will be integrated with hard-infrastructure improvements to establish approaches that will be robust in the face of natural hazards and climate-change scenarios. Priority areas include the Route 9/126 intersection, the CSX culvert near Landham Pond Dam, and the Singletary Lane culvert. | Complete | Culvert assessment report has been completed. | Completed.
2 | Conduct a flooding study of the Walnut Street neighborhood to assess flooding impacts in more detail and identify potential flood mitigation projects. Note that flooding in the Walnut Street neighborhood is connected to Route 9/126 flooding, so a larger watershed approach may be appropriate to best address these related issues. | Complete | Study Complete. Design of stream restoration and school path improvements is nearly complete. Application submitted for MVP grant to construct. | Completed.
3 | Acquire the CSX corridor and implement next steps to develop the Bruce Freeman Rail Trail at the site. Address problems related to historically undersized culverts and neighborhood flooding. Partner with the Town of Sudbury to develop acquisition and trail development plans through a regional approach. | In Progress | Purchase should be complete by October 2022. $408,000 Mass Trails grant has been received for both Bruce Freeman and Chris Walsh Trails, and NPS Grant has been acquired. Currently negotiating 3.5 miles of property and hoping to close on an acquisition in the near future. | Carried directly into HMP Update.
4 | Assess flood-proofing measures and flood storage to prevent future flooding at critical facilities, including the Callahan Senior Center and Fire Station #7. | In Progress | Floodproofing measures have been installed across facilities over time. At least several municipal facilities, such as the Callahan Senior Center and Fire Station #7 still experience flooding issues. Additional improvements associated with development of the area surrounding Fire Station #7 are anticipated to result in stormwater infrastructure improvements provide additional flooding relief. | Carried directly into HMP Update.
5 | Perform a risk assessment of vulnerable pump stations and establish priority actions for reducing potential flooding impacts, including consideration of nature-based solutions or green infrastructure approaches. Establish emergency back-up plans for the pump stations. Continue to implement improvements to reduce infiltration and inflow. | In Progress | Inflow and infiltration is continuously being improved year after year with our pipe lining plan through our sewer defects capital appropriation as well as in house operations maintenance and repairs. As far as back up plans regarding flooding, more progress can be made. The City has backup plans for power outages and pump and equipment failures. | Removed; Assessed by DPW on a regular basis as part of their core efforts.
6 | Assess drainage infrastructure and drainage-driven road flooding and develop green infrastructure solutions for stormwater management to be used in tandem with improvements to the outdated and undersized stormwater system to reduce road flooding and problems with ice slicks that make roads dangerous or impassable during hazard events. Develop a list of specific priorities, assess feasibility and cost, rank priority projects in terms of climate resilience potential, and develop concept designs for key projects. For linear projects along the City’s roadways, consider utilizing green infrastructure design resources developed for other parts of the region, such as the Rhode Island Department of Transportation’s Linear Stormwater Manual, released in 2019. | In Progress | DPW has been implementing green infrastructure to mitigate flooidng issues as opportunities arise with other site improvement projects. The City is also coordinating with MassDOT on draingage improvements that they are doing on Route 9, anticipated to be complete in 2022. | Integrated into: "Develop green infratructure on municipal properties to improve stormwater management and reduce heat island impacts."
7 | Implement recommendations from the feasibility study for removal of Landham Pond Dam, including purchase of the rail corridor and removal or rehabilitation of existing culverts. | In Progress | Contingent upon acqusition of rail trail (recommendation item 5). | Carried directly into HMP Update.
8 | Evaluate satellite locations to supplement DPW operations center and salt storage in order to provide better support City-wide and reduce response times. | No Update | Discussions have been underway, but there have been no recent efforts to evaluate satellite locations to supplement the DPW operations center and salt storage. | Carried directly into HMP Update.
9 | Implement plans to install air conditioning in Framingham schools that currently lack A/C, with the high school as the most immediate priority. Include any necessary upgrades to the electrical infrastructure to allow for the additional capacity required to run air conditioning systems. This will also expand the number of public buildings available for cooling stations. | In Progress | AC deployment at FHS has been completed. AC deployment across other schools is currently underway starting with McCarthy Elementary School. FPS is working on assessing and upgrading electrical capacity across facilities and installing temporary cooling equipment for buildings that do not currently have cooling. Energy efficienct heat pump equipment that provides electric heating and cooling has been prioritized for these replacements. | Integrated into: "Utilize clean energy technologies to provide efficient heating and cooling capacity to municpal facilities and schools. "
10 | Plan and post neighborhood and regional evacuation routes, with particular attention to the needs of homeless and elderly populations and Environmental Justice communities. Consider feasibility of installing second parking lot entrance/exit from Callahan Senior Center to allow use as a warming/cooling center, including whether proximity of the lot to the nearby bridge will allow for this improvement. | In Progress | A second entrance/exit to the Callahan Senior Center cannot be added. Exercise done to evaluate risk to low-lying properties from potential dam failures (3-4 years ago). Route-9 improvements with the MA DOT will help ensure that a critical roadway for evacuation is available that might otherwise be cut off due to severe flooding. | Integrated into: "Plan and post neighborhood and regional evacuation routes."
11 | Evaluate opportunities to provide emergency backup power to critical facilities, including feasibility of green power and battery storage. City-wide, there are a number of buildings and facilities (including substations, schools, Framingham Housing Authority properties, etc.) in need of backup power systems that could be tied to renewable or alternative energy sources to protect public buildings and infrastructure from freezing and improve services for residents who may lose power during emergencies or hazard events. | In Progress | Energy resiliency studies have been completed at multiple municipal locations including City Hall, the Police Department Headquarters, A Street Pumping Station, Framingham High School, Fuller Middle School, McCarthy Elementary School, FHA properties, and the Farley Building. City is exploring how to procure clean energy resiliency assets for municipal facilities in connection with this work. | Integrated into: "Evaluate and pursue opportunities to use clean energy technologies, such as microgrids, to provide enhanced backup power to municipal facilities."
12 | Assess additional mosquito/pest control options, including increased stormwater BMP maintenance, integrated pest management approaches, determination of future risks due to increase in type and quantity of pests/disease vectors due to climate change, and continued development and implementation of education and outreach programs. | In Progress | Many efforts delayed due to COVID-19 pandemic, last municipal efforts from MVP report. However, updated mosquito and tick information is prvoided on the municipal website: https://www.framinghamma.gov/3016/Mosquitoes-Ticks. | Carried directly into HMP Update.
13 | Conduct a feasibility study to evaluate development of a stormwater utility. | Cancelled | Not currently under consideration. | Removed.
14 | Identify vulnerable populations and foster an improved communications network in advance of a hazard event to facilitate communication efforts and outreach to those most in need of information and assistance. Evaluate feasibility of a combined Fire/Police/DPW dispatch. Utilize networks of existing groups to encourage communication efforts led by churches, schools, social groups, or City agencies. Focus should be on populations that may be more vulnerable to climate-induced risks, such as extreme temperatures, may lack appropriate shelter during increasingly intense storms, or that may be unprepared if stranded or cut off from supplies due to flooding or storm events. Residents of South Framingham were a particular concern with regard to potential language barriers and ability to access transportation resources during hazards. Determine which other communities and populations are most likely to be impacted by different hazards and assess specific translation needs for messaging. Develop a plan to overcome internal communication barriers within City departments and between the City and community partners or residents. Improve outreach and education efforts to ensure City residents, especially vulnerable populations and residents for whom English is not a first language, can access accurate and up-to-date emergency information, shelters, heating and cooling centers, evacuation routes, provisions and services during emergencies. Identifying opportunities to improve the resiliency of our communications networks, such as with local cell towers, will improve the effectiveness of outreach efforts in emergency events. | In Progress | Stronger community engagement is currently moving forward through the Metro West Climate Equity project which is supporting the City in building stronger relationships with EJ neighborhoods in Framingham. It is anticipated that the outreach strategies through this project will help inform community engagement strategies through other municipal projects. Evaluation of combined dispatch is underway. Fire Department moving forward on planning, identifying potential location and design. The City is targeting the next couple of years to find property and begin construcitng the new combined dispatch center which may be regional in nature. Within the Fire Department, efforts are underway to support residents with disabilities in emergencies and the Department has conducted training, supported by the City's ADA Coordinator. Training occured several months ago. The City uses reverse 911 system, implemented approximately 3-4 years ago. Residents can signup for email and text notifications. A new radio system has also been implemented for Police, Fire, and Emergency (went into operation last year). There are plans to improve system in terms of coverage area and communications resilience. Recent upgrades have already improved coverage area for radio communication singificantly. | Integrated into: "Foster an improved communications network to better reach vulnerable populations and those most in need of information and assistance."
15 | Improve the resiliency and passive survivability of local buildings and facilities through energy efficiency and adoption of clean energy. Implement renewable/alternative energy technologies and energy efficiency measures in new and existing facilities across the public and private sectors to assist in reducing the impacts of extreme temperatures encountered in heatwaves and freezing periods, minimizing the strain on electric grid and other fuel sources during such hazards, improving the reliability energy-using equipment, and mitigating the local contribution to climate change and the prevalence of associated impacts. | In Progress | This work is underway, supported through both municipal-focused and community-focused programs. Municipal energy efficiency projects (such as insulation and weatherization projects) through the Green Communities program have helped to reduce municipal energy consumption. Programs have been developed to offer residents and businesses opportunities to improve their efficiency and to adopt renewable energy (including the City's participation in the Mass Save Municipal Partnership Program and the MetroWest Solar + Clean Heat Challenge it completed). Solar has been installed at the McAuliffe Library and Brophy Elementary School, and solar + battery storage is being installed at the Fuller Middle School. Additional efforts in this area are in development (see item 13 for related information on this measure). | Integrated into: "Evaluate and pursue opportunities to use clean energy technologies, such as microgrids, to provide enhanced backup power to municipal facilities."
Moderate Priority
17 | Develop and implement plans for ecological restoration at Beaver Dam Brook. | In Progress | City is coordinating with Eversource on its extensive remediation project at 350 Irving Street. The City is advocating for ecological and wetlands restoration to be done as part of this remediation work. Eversource will be removing contaminated sediments and in this process will be remediating some wetlands property. | Integrated into: "Protect and restore wetland areas, including around Lake Waushakum."
18 | Conduct a study of flooding along Beaver Dam Brook, focusing in particular on the Second Street and Taralli Terrace Bridge area. | In Progress | Previously incorporated in Phase I Stormwater Master Plan 2008. Seeking to have updated as part of Comprehensive Stormwater Master Plan. Both bridges are also targeted for replacement as part of the long-range capital plan. | Integrated into "Develop a Comprehensive Stormwater Master Plan."
19 | Design and implement flood mitigation and drainage improvements in the Hemenway neighborhood. | In Progress | A major component of this work is contingent upon acqusition of the rail trail. | Integrated into: "Protect or acquire private property impacted by flooding in repetitive loss neighborhoods."
20 | Assess levels and sources of stream contaminants in floodplain areas. Build on knowledge of existing problem areas (e.g. 350 Irving and General Chemical) and locate other above- and below-ground sources with potential to contaminate floodwaters. | In Progress | DPW is performing catchment and drainage inspections to identify potential contaminants in an effort to improve stormwater quality and compliance with MS4 permitting. Eversource's remediation project at 350 Irving Street will also support this measure. More contamination was found during the Beaver Street Bridge Replacement. Through the 350 Irving Street project, dredging will occur from Mary Dennison and all the way upstream to Irivng Street. Excavation and retoration of wetlands will be occuring at 350 Irving Street. Eversource will also be performing subsurface remediation activities to limit the movement of contamination into the wetlands. | Removed: Progress is underway.
21 | Conduct a comprehensive assessment of water quality, supply, and infrastructure, including assessment of aging infrastructure, such as the MWRA aqueducts. Examine potential for incorporating homes with private wells (particularly in the northwest portion of the City) into the City water supply system. Explore means of mitigating climate-driven impacts on public water supply sources, such as harmful algal blooms or drought. | In Progress | Extending water mains to the northwest portion of the City - may not have been looked at in depth but would be a very costly project for the City to take on. Water & Sewer has prioritized aging infrastructure based on age, risk of failure, fire flow, and water quality to update our Capital plan for outyears. MWRA infrastructure is not assssed as it is understood that they do this on their own. Framingham does not have its own source of public water supply currently. All of the City's water comes from the MWRA so the MWRA would be primarily responsible for mitigating impacts on supply sources. | Transformed into: "Explore intermunicipal connections with neighboring communities for water resources."
22 | Assess public and private dams and develop designs for improvements/replacement where necessary. Assessment should include updating information on ownership and gaining an understanding of condition, as well as determining risks and priority projects. Saxonville Dam, though privately owned by Saxonville Mills, was raised by workshop participants as a specific area of concern. Coordinate with private dam owners to determine where viable partnerships may exist that would provide important flood mitigation benefits to the City. | No Update | The City owns two dams but does not have significant invovlement with private dams throughout the City. No udpates on this measure. | Integrated into: "Assess City-owned dams and engage other public and private dam owners in Framingham on resilience. "
23 | Develop a City-wide comprehensive tree and forest management program to identify, remove, and replace problem trees, preserve intact forests and street tree cover, provide guidance and resources for gradually moving toward more climate-resilient trees and forest communities (e.g. species that will tolerate warmer temperatures) and develop guidelines to manage conversion of forest land and require shade tree plantings in new developments to promote erosion control and improved infiltration. | Delayed | While no definitive plan is in place, the City is maintaining its current management of an estimated 12,000 street streets as well as other vegetation in the public right of way. These efforts include conducting hazardous tree assessments, prescribing treatment, and overseeing tree removals. Framingham’s 2020 Master Plan Update places priority on development of standards for green infrastructure as part of site and road improvements as well as other zoning criteria. | Carried directly into HMP Update.
24 | Establish a water conservation program to reduce MWRA purchases and increase drought resilience for residents and the City. | In Progress | Progress has been made through public education of water conservation. DPW has been promoting water efficiency through its social media. | Carried directly into HMP Update.
25 | Develop comprehensive plan for beaver management to mitigate against unpredictable flooding/impoundment impacts. Establish creative engineering solutions, identify suitable areas for beaver relocation or where beaver activity may be creating flood storage that contributes to resiliency, and consider the development of special legislation to give the City authority to address problematic beaver dams on private property. Evaluate permitting feasibility of beaver deceivers or other non-lethal methods to mitigating the flood impact of problem beavers in flood-prone areas. | Delayed | Progress not started; City will be exploring potential solutions. | Carried directly into HMP Update.
26 | Continue upgrading aging traffic control systems with more energy efficient and resilient options such as low voltage LED lights with back-up power supply to maintain normal traffic flow operations during power outages. | In Progress | Replacement of traffic lights with LEDs is nearly complete (likely over 90%). City could expand upon this effort through the inclusion of battery backup. | Removed; Almost complete. | Shawn: According to Pat at the DPW, the overwhelming majority of traffic lights are LED and were before the MVP report. He estimated at least over 90% but likely close to all of them are LED at this point. Kross: This should include battery back-up for operation through power outages.
27 | Develop a City-wide Business Resilience Plan to support local businesses and make the business community more resilient. Identify business development areas where impacts from climate hazards can be easily avoided or mitigated (e.g., by avoiding floodplains or areas of known drainage-related flooding) and targeted improvements, such as a microgrid and rooftop solar installations, employed to provide extra resilience to community businesses in the Downtown and I-90 Exits 12 and 13 areas. Evaluate feasibility of a carpool lane to these key exits. | Delayed | A City-wide Business Resilience Plan centered on hazard mitigation is not underway, but a plan for COVID-19 recovery was recently completed. While not focused on local businesses, the City has developed energy esiliency studies of three locations in the community. The City is pursuing grant funding to implement a parking garage behind the City Hall. Implementation of a parking garage behind City Hall will provide additional resilience with the integration of EV charging stations. The parking garage could be paired with battery storage to provide resilient charging solutions. Implementation of the parking garage could also improve accessibility to the City Hall. | Carried directly into HMP Update.
28 | Conduct a microgrid feasibility study to investigate the possibility of localized power for critical facilities and ensure that electrical services continue when the primary power grid is disrupted by a hazard event. Identify and implement measures to prepare municipal facilities and operations to be more energy independent, including repairing/replacing rooftops in order to support solar energy systems and adopting alternative fuel vehicles. | Complete | Three energy resiliency studies have been completed for different areas of the community, with more anticipated to be on the way. The City is continually working to identify and implement measures to municipal facilities and operations to be more energy independent. See item 13 for more information. | Stated measure complete, expanded measure integrated into: "Evaluate and pursue opportunities to use clean energy technologies, such as microgrids, to provide enhanced backup power to municipal facilities."
29 | Partner with electric and gas utility providers to identify and address vulnerabilities in utility infrastructure and enhance communication and cooperation between the City and private utilities. Continue to coordinate tree maintenance to increase resilience to severe weather. Continue to utilize programs and resources offered by utilities and their associated service providers to improve energy resiliency for municipal facilities as well as residents and local businesses. | Continuous | The City has maintained consistent communication with the utilities on a variety of energy programs (Ex. Eversource Geothermal Pilot Program and Mass Save Community First Partnership Program) | Integrated into: "Partner with the local utility on climate resilience efforts."
30 | Coordinate regional management efforts of Lake Cochituate, including studying ways to reduce pesticide and nutrient inputs from stormwater runoff. Efforts can include public outreach and education. | In Progress | Framingham is participating in an MVP Project titled the Sudbury-Assabet-Concord Natural Climate Solutions Grant that will support nature-based solutions. | Integrated into: "Coordinate regional management efforts of Lake Cochituate."
31 | Update flood mapping throughout the City to ensure that residents and businesses have the most accurate information regarding risks and the need for potential mitigation strategies. | No Update | Flood maps are updated by FEMA, unclear of current flood map update status. | Removed.
32 | Conduct robust transportation resiliency planning to ensure that access is maintained in and out of the City and throughout the Metro West region during hazard events. Focus on 1) facilitating emergency operations, 2) studying key junctions such as Exit 13, Exit 12, and the Route 9/126 intersection, and 3) considering approaches to improve and promote public transportation to help reduce cars on the road during inclement weather and reduce greenhouse gas emissions. | In Progress | Phase II of Transportation Master Plan completed in 2022. The City is also working on implementing public EV charging infrastructure to enourage residents to adopt electric vehicles. Implementation of a Downtown Parking Garage could support the community. | Integrated into: "Conduct robust transportation resiliency planning."
33 | Assess feasibility and funding options for property acquisitions along the Sudbury River and other flood-prone areas in the City with the intent of providing relief for property owners facing potential flood risks or repetitive losses and increasing available space for floodplain restoration to reduce flood impacts. | Delayed | Framingham is participating in an MVP Project titled the Sudbury-Assabet-Concord Natural Climate Solutions Grant that will support nature-based solutions. It is anticipated that this work could support the assessment of feasibility and funding options. | Integrated into: "Protect or acquire private property impacted by flooding in repetitive loss neighborhoods." | Why would properties need to be acquired? Shawn: According to the MVP report, areas downstream of dams on the Sudbury River would be threatened by floodwaters from a dam failure. Areas along the Sudbury River were noted as priority targets for improved riparian flood storage.
34 | Coordinate with Framingham State University, MassBay Community College, and local community organizations to develop educational messaging and/or programming to transfer climate change risk and vulnerability knowledge to the general public, especially future generations. | Continuous | The City coordinates with Framingham State Unviersity (FSU) and Mass Bay Community College. For example, there is current coordination with Sustainability Coordinator and FSU on a student program to explore heat islands in Framingham. Coordination with local community organizations are in development. This measure is also supported by the MVP Climate Equity Project that Framingham is working on and will be further supported through the City's Climate Action Plan. | Integrated into : "Coordinate local community organizations to develop educational messaging and/or programming to transfer climate change risk and vulnerability knowledge to the general public."
Lower Priority
36 | Continue to support coordinated efforts to provide emergency shelters that effectively serve Framingham’s population during hazard events, including cooling and warming centers. Begin a City-wide discussion about informal sheltering to better understand how and when residents might use shelter services and redefine ‘sheltering’ to meet Framingham’s specific needs. For instance, if primary shelter use is for charging stations, develop locations where residents can meet this need during power outages without the expense of opening formal shelters. Consider how to support the use of informal sheltering locations where people already go in emergencies. | In Progress | The City continues to provide emergency shelters for heating and cooling during severe weather in summer and winter months. | Carried directly into HMP Update. | Unrelated to this specific measure, plans were developed during COVID-19 for temprorary mortuaries, which can be important to preserving the capacity of critical resources such as emergency rooms at the local hospital in future emergencies.
37 | Evaluate feasibility of City ordinance for private maintenance of problem trees. Such an ordinance can help increase utility resilience by reducing branch and tree falls during severe weather. | No Update | The City does not have an ordinance for the private maintenance of problem trees. | Intetegrated into: "Develop a citywide comprehensive tree and forest management program."
38 | Explore and evaluate means of improving resiliency at historic properties throughout the City. | In Progress | Improvements to municipal historical buildings, such as the Old Edgell Library, are currently in progress through capital projects. It is possible that the the CPA may be able to provide additional support for local historic properties throughout the community. | Carried directly into HMP Update.
39 | Identify financial and technical assistance for MS4 implementation, to support municipal departments in complying with the MS4 permit. | Ongoing | Framingham has submitted by three annual reports for MS4 regarding BMPs. Annual reports detail technical assistance that Framingham has received to supprot MS4 implementation. The City is continually looking for financial assistance to support compliance with the MS4 permits. | Removed; this action is integrated as part of general proejct development for each relevant measure.
40 | Investigate potential for setting up and funding an emergency fund to support financially vulnerable populations during climate change related hazards and emergencies. This could include a surcharge on tax bills | Removed | Framingham has implemented temproary financial assistance to families due to COVID-19, supporting many residents that are also highly vulnerable to climate change impacts. There are no current plans for a long-standing emergency fund covered by tax bills. | Removed.
41 | Collaborate with the state women’s prison, MCI-Framingham, to evaluate potential climate impacts related to hazard events such as flooding, drought and extreme heat. Assess resiliency of the prison facility. | Removed | The State is currently evaluating the potential to replace MCI Framingham. All emergency plans of MCI-Framingham need to be approved by the Fire Chief annually. There is coordination with MCI Framingham on various issues. | Removed.
42 | Coordinate with MWRTA and MBTA to assess resiliency of commuter transportation, with particular focus on minimizing susceptibility to climate hazards and ensuring continued operations. Incorporate assessment of increased ridership and expanded offerings that would better connect employees with key business centers. | Continuous | The City has been engaged with MWRTA in several recent planning processes to identify opportunities to support public transportation options including the 2022 Transportation Master Plan. FD has maintained discussions with MWRTA for MWRTA to provide local transportation options in the event of an emergency. | Integrated into: "Conduct robust transportation resiliency planning."
43 | Communicate with MEMA regarding the vulnerability of its command center and make efforts to increase the resiliency and safety of state emergency operations. | Removed | N/A | Removed.
44 | Facilitate education for prospective homebuyers and realtors to address flood risks to make sure that buyers are aware of what it means to purchase a home that may be located in or near a floodplain and educate residents on protections such as flood insurance that can mitigate financial risks associated with climate hazards. Target landlord associations and realtors to encourage risk communication. | Delayed | The City is currently evaluating opportunities to educate property owners about this issue. | Carried directly into HMP Update.

## MVP Recommendations WIP (hidden)
MVP Recommendation | Current Status | Current Status Description/Explanation | Notes / Comments (Provide feedback as to whether will be moving forward or not)
Highest Priority
Conduct a field inventory of culverts and bridges to rank and prioritize projects for increased flooding resiliency and storm-hardening, followed by design and implementation of priority resizing or replacement projects. Green infrastructure, Low-Impact Design, and other nature-based solutions will be integrated with hard-infrastructure improvements to establish approaches that will be robust in the face of natural hazards and climate-change scenarios. Priority areas include the Route 9/126 intersection, the CSX culvert near Landham Pond Dam, and the Singletary Lane culvert. | Complete | Culvert assessment report has been completed.
Conduct a flooding study of the Walnut Street neighborhood to assess flooding impacts in more detail and identify potential flood mitigation projects. Note that flooding in the Walnut Street neighborhood is connected to Route 9/126 flooding, so a larger watershed approach may be appropriate to best address these related issues. | Complete | Study Complete. Design of stream restoration and school path improvements is nearly complete. Application submitted for MVP grant to construct.
Acquire the CSX corridor and implement next steps to develop the Bruce Freeman Rail Trail at the site. Address problems related to historically undersized culverts and neighborhood flooding. Partner with the Town of Sudbury to develop acquisition and trail development plans through a regional approach. | In Progress | Purchase should be complete by October 2022. $408,000 Mass Trails grant has been received for both Bruce Freeman and Chris Walsh Trails, and NPS Grant has been acquired. Currently negotiating 3.5 miles of property and hoping to close on an acquisition in the near future.
Assess flood-proofing measures and flood storage to prevent future flooding at critical facilities, including the Callahan Senior Center and Fire Station #7. | In Progress | Floodproofing measures have been installed across facilities over time. At least several municipal facilities, such as the Callahan Senior Center and Fire Station #7 still experience flooding issues. Additional improvements associated with development of the area surrounding Fire Station #7 are anticipated to result in stormwater infrastructure improvements provide additional flooding relief.
Perform a risk assessment of vulnerable pump stations and establish priority actions for reducing potential flooding impacts, including consideration of nature-based solutions or green infrastructure approaches. Establish emergency back-up plans for the pump stations. Continue to implement improvements to reduce infiltration and inflow. | In Progress | Inflow and infiltration is continuously being improved year after year with our pipe lining plan through our sewer defects capital appropriation as well as in house operations maintenance and repairs. As far as back up plans regarding flooding, more progress can be made. The City has backup plans for power outages and pump and equipment failures. | DPW already performs this work on a regular basis.
Assess drainage infrastructure and drainage-driven road flooding and develop green infrastructure solutions for stormwater management to be used in tandem with improvements to the outdated and undersized stormwater system to reduce road flooding and problems with ice slicks that make roads dangerous or impassable during hazard events. Develop a list of specific priorities, assess feasibility and cost, rank priority projects in terms of climate resilience potential, and develop concept designs for key projects. For linear projects along the City’s roadways, consider utilizing green infrastructure design resources developed for other parts of the region, such as the Rhode Island Department of Transportation’s Linear Stormwater Manual, released in 2019. | In Progress | DPW has been implementing green infrastructure to mitigate flooidng issues as opportunities arise with other site improvement projects. The City is also coordinating with MassDOT on draingage improvements that they are doing on Route 9, anticipated to be complete in 2022. | Incorporated as part of Action 28 (Green Infrastructure)
Implement recommendations from the feasibility study for removal of Landham Pond Dam, including purchase of the rail corridor and removal or rehabilitation of existing culverts. | In Progress | Contingent upon acqusition of rail trail (recommendation item 5).
Evaluate satellite locations to supplement DPW operations center and salt storage in order to provide better support City-wide and reduce response times. | No Update | Discussions have been underway, but there have been no recent efforts to evaluate satellite locations to supplement the DPW operations center and salt storage.
Implement plans to install air conditioning in Framingham schools that currently lack A/C, with the high school as the most immediate priority. Include any necessary upgrades to the electrical infrastructure to allow for the additional capacity required to run air conditioning systems. This will also expand the number of public buildings available for cooling stations. | In Progress | AC deployment at FHS has been completed. AC deployment across other schools is currently underway starting with McCarthy Elementary School. FPS is working on assessing and upgrading electrical capacity across facilities and installing temporary cooling equipment for buildings that do not currently have cooling. Energy efficienct heat pump equipment that provides electric heating and cooling has been prioritized for these replacements.
Plan and post neighborhood and regional evacuation routes, with particular attention to the needs of homeless and elderly populations and Environmental Justice communities. Consider feasibility of installing second parking lot entrance/exit from Callahan Senior Center to allow use as a warming/cooling center, including whether proximity of the lot to the nearby bridge will allow for this improvement. | In Progress | A second entrance/exit to the Callahan Senior Center cannot be added. Exercise done to evaluate risk to low-lying properties from potential dam failures (3-4 years ago). Route-9 improvements with the MA DOT will help ensure that a critical roadway for evacuation is available that might otherwise be cut off due to severe flooding.
Evaluate opportunities to provide emergency backup power to critical facilities, including feasibility of green power and battery storage. City-wide, there are a number of buildings and facilities (including substations, schools, Framingham Housing Authority properties, etc.) in need of backup power systems that could be tied to renewable or alternative energy sources to protect public buildings and infrastructure from freezing and improve services for residents who may lose power during emergencies or hazard events. | In Progress | Energy resiliency studies have been completed at multiple municipal locations including City Hall, the Police Department Headquarters, A Street Pumping Station, Framingham High School, Fuller Middle School, McCarthy Elementary School, FHA properties, and the Farley Building. City is exploring how to procure clean energy resiliency assets for municipal facilities in connection with this work.
Assess additional mosquito/pest control options, including increased stormwater BMP maintenance, integrated pest management approaches, determination of future risks due to increase in type and quantity of pests/disease vectors due to climate change, and continued development and implementation of education and outreach programs. | In Progress | Many efforts delayed due to COVID-19 pandemic, last municipal efforts from MVP report. However, updated mosquito and tick information is prvoided on the municipal website: https://www.framinghamma.gov/3016/Mosquitoes-Ticks.
Conduct a feasibility study to evaluate development of a stormwater utility. | Cancelled | Not currently under consideration.
Identify vulnerable populations and foster an improved communications network in advance of a hazard event to facilitate communication efforts and outreach to those most in need of information and assistance. Evaluate feasibility of a combined Fire/Police/DPW dispatch. Utilize networks of existing groups to encourage communication efforts led by churches, schools, social groups, or City agencies. Focus should be on populations that may be more vulnerable to climate-induced risks, such as extreme temperatures, may lack appropriate shelter during increasingly intense storms, or that may be unprepared if stranded or cut off from supplies due to flooding or storm events. Residents of South Framingham were a particular concern with regard to potential language barriers and ability to access transportation resources during hazards. Determine which other communities and populations are most likely to be impacted by different hazards and assess specific translation needs for messaging. Develop a plan to overcome internal communication barriers within City departments and between the City and community partners or residents. Improve outreach and education efforts to ensure City residents, especially vulnerable populations and residents for whom English is not a first language, can access accurate and up-to-date emergency information, shelters, heating and cooling centers, evacuation routes, provisions and services during emergencies. Identifying opportunities to improve the resiliency of our communications networks, such as with local cell towers, will improve the effectiveness of outreach efforts in emergency events. | In Progress | Stronger community engagement is currently moving forward through the Metro West Climate Equity project which is supporting the City in building stronger relationships with EJ neighborhoods in Framingham. It is anticipated that the outreach strategies through this project will help inform community engagement strategies through other municipal projects. Evaluation of combined dispatch is underway. Fire Department moving forward on planning, identifying potential location and design. The City is targeting the next couple of years to find property and begin construcitng the new combined dispatch center which may be regional in nature. Within the Fire Department, efforts are underway to support residents with disabilities in emergencies and the Department has conducted training, supported by the City's ADA Coordinator. Training occured several months ago. The City uses reverse 911 system, implemented approximately 3-4 years ago. Residents can signup for email and text notifications. A new radio system has also been implemented for Police, Fire, and Emergency (went into operation last year). There are plans to improve system in terms of coverage area and communications resilience. Recent upgrades have already improved coverage area for radio communication singificantly.
Improve the resiliency and passive survivability of local buildings and facilities through energy efficiency and adoption of clean energy. Implement renewable/alternative energy technologies and energy efficiency measures in new and existing facilities across the public and private sectors to assist in reducing the impacts of extreme temperatures encountered in heatwaves and freezing periods, minimizing the strain on electric grid and other fuel sources during such hazards, improving the reliability energy-using equipment, and mitigating the local contribution to climate change and the prevalence of associated impacts. | In Progress | This work is underway, supported through both municipal-focused and community-focused programs. Municipal energy efficiency projects (such as insulation and weatherization projects) through the Green Communities program have helped to reduce municipal energy consumption. Programs have been developed to offer residents and businesses opportunities to improve their efficiency and to adopt renewable energy (including the City's participation in the Mass Save Municipal Partnership Program and the MetroWest Solar + Clean Heat Challenge it completed). Solar has been installed at the McAuliffe Library and Brophy Elementary School, and solar + battery storage is being installed at the Fuller Middle School. Additional efforts in this area are in development (see item 13 for related information on this measure).
Moderate Priority
Develop and implement plans for ecological restoration at Beaver Dam Brook. | In Progress | City is coordinating with Eversource on its extensive remediation project at 350 Irving Street. The City is advocating for ecological and wetlands restoration to be done as part of this remediation work. Eversource will be removing contaminated sediments and in this process will be remediating some wetlands property. | Incroporated as part of Action 26
Conduct a study of flooding along Beaver Dam Brook, focusing in particular on the Second Street and Taralli Terrace Bridge area. | In Progress | Previously incorporated in Phase I Stormwater Master Plan 2008. Seeking to have updated as part of Comprehensive Stormwater Master Plan. Both bridges are also targeted for replacement as part of the long-range capital plan.
Design and implement flood mitigation and drainage improvements in the Hemenway neighborhood. | In Progress | A major component of this work is contingent upon acqusition of the rail trail.
Assess levels and sources of stream contaminants in floodplain areas. Build on knowledge of existing problem areas (e.g. 350 Irving and General Chemical) and locate other above- and below-ground sources with potential to contaminate floodwaters. | In Progress | DPW is performing catchment and drainage inspections to identify potential contaminants in an effort to improve stormwater quality and compliance with MS4 permitting. Eversource's remediation project at 350 Irving Street will also support this measure. More contamination was found during the Beaver Street Bridge Replacement. Through the 350 Irving Street project, dredging will occur from Mary Dennison and all the way upstream to Irivng Street. Excavation and retoration of wetlands will be occuring at 350 Irving Street. Eversource will also be performing subsurface remediation activities to limit the movement of contamination into the wetlands.
Conduct a comprehensive assessment of water quality, supply, and infrastructure, including assessment of aging infrastructure, such as the MWRA aqueducts. Examine potential for incorporating homes with private wells (particularly in the northwest portion of the City) into the City water supply system. Explore means of mitigating climate-driven impacts on public water supply sources, such as harmful algal blooms or drought. | In Progress | Extending water mains to the northwest portion of the City - may not have been looked at in depth but would be a very costly project for the City to take on. Water & Sewer has prioritized aging infrastructure based on age, risk of failure, fire flow, and water quality to update our Capital plan for outyears. MWRA infrastructure is not assssed as it is understood that they do this on their own. Framingham does not have its own source of public water supply currently. All of the City's water comes from the MWRA so the MWRA would be primarily responsible for mitigating impacts on supply sources. | Not clear whether this will be of use given that the MWRA controls Framingham current water resources.
Assess public and private dams and develop designs for improvements/replacement where necessary. Assessment should include updating information on ownership and gaining an understanding of condition, as well as determining risks and priority projects. Saxonville Dam, though privately owned by Saxonville Mills, was raised by workshop participants as a specific area of concern. Coordinate with private dam owners to determine where viable partnerships may exist that would provide important flood mitigation benefits to the City. | No Update | The City owns two dams but does not have significant invovlement with private dams throughout the City. No udpates on this measure.
Develop a City-wide comprehensive tree and forest management program to identify, remove, and replace problem trees, preserve intact forests and street tree cover, provide guidance and resources for gradually moving toward more climate-resilient trees and forest communities (e.g. species that will tolerate warmer temperatures) and develop guidelines to manage conversion of forest land and require shade tree plantings in new developments to promote erosion control and improved infiltration. | Delayed | While no definitive plan is in place, the City is maintaining its current management of an estimated 12,000 street streets as well as other vegetation in the public right of way. These efforts include conducting hazardous tree assessments, prescribing treatment, and overseeing tree removals. Framingham’s 2020 Master Plan Update places priority on development of standards for green infrastructure as part of site and road improvements as well as other zoning criteria.
Establish a water conservation program to reduce MWRA purchases and increase drought resilience for residents and the City. | In Progress | Progress has been made through public education of water conservation. DPW has been promoting water efficiency through its social media.
Develop comprehensive plan for beaver management to mitigate against unpredictable flooding/impoundment impacts. Establish creative engineering solutions, identify suitable areas for beaver relocation or where beaver activity may be creating flood storage that contributes to resiliency, and consider the development of special legislation to give the City authority to address problematic beaver dams on private property. Evaluate permitting feasibility of beaver deceivers or other non-lethal methods to mitigating the flood impact of problem beavers in flood-prone areas. | Delayed | Progress not started; City will be exploring potential solutions.
Continue upgrading aging traffic control systems with more energy efficient and resilient options such as low voltage LED lights with back-up power supply to maintain normal traffic flow operations during power outages. | In Progress | Replacement of traffic lights with LEDs is nearly complete (likely over 90%). City could expand upon this effort through the inclusion of battery backup. | Shawn: According to Pat at the DPW, the overwhelming majority of traffic lights are LED and were before the MVP report. He estimated at least over 90% but likely close to all of them are LED at this point. Kross: This should include battery back-up for operation through power outages. | Almost complete, removing from list
Develop a City-wide Business Resilience Plan to support local businesses and make the business community more resilient. Identify business development areas where impacts from climate hazards can be easily avoided or mitigated (e.g., by avoiding floodplains or areas of known drainage-related flooding) and targeted improvements, such as a microgrid and rooftop solar installations, employed to provide extra resilience to community businesses in the Downtown and I-90 Exits 12 and 13 areas. Evaluate feasibility of a carpool lane to these key exits. | Delayed | A City-wide Business Resilience Plan centered on hazard mitigation is not underway, but a plan for COVID-19 recovery was recently completed. While not focused on local businesses, the City has developed energy esiliency studies of three locations in the community. The City is pursuing grant funding to implement a parking garage behind the City Hall. Implementation of a parking garage behind City Hall will provide additional resilience with the integration of EV charging stations. The parking garage could be paired with battery storage to provide resilient charging solutions. Implementation of the parking garage could also improve accessibility to the City Hall.
Conduct a microgrid feasibility study to investigate the possibility of localized power for critical facilities and ensure that electrical services continue when the primary power grid is disrupted by a hazard event. Identify and implement measures to prepare municipal facilities and operations to be more energy independent, including repairing/replacing rooftops in order to support solar energy systems and adopting alternative fuel vehicles. | In Progress | Three energy resiliency studies have been completed for different areas of the community, with more anticipated to be on the way. The City is continually working to identify and implement measures to municipal facilities and operations to be more energy independent. See item 13 for more information. | Incorporated as part of Action 23 (Clean Energy Assets)
Partner with electric and gas utility providers to identify and address vulnerabilities in utility infrastructure and enhance communication and cooperation between the City and private utilities. Continue to coordinate tree maintenance to increase resilience to severe weather. Continue to utilize programs and resources offered by utilities and their associated service providers to improve energy resiliency for municipal facilities as well as residents and local businesses. | Continuous | The City has maintained consistent communication with the utilities on a variety of energy programs (Ex. Eversource Geothermal Pilot Program and Mass Save Community First Partnership Program)
Coordinate regional management efforts of Lake Cochituate, including studying ways to reduce pesticide and nutrient inputs from stormwater runoff. Efforts can include public outreach and education. | In Progress | Framingham is participating in an MVP Project titled the Sudbury-Assabet-Concord Natural Climate Solutions Grant that will support nature-based solutions.
Update flood mapping throughout the City to ensure that residents and businesses have the most accurate information regarding risks and the need for potential mitigation strategies. | No Update | Flood maps are updated by FEMA, unclear of current flood map update status.
Conduct robust transportation resiliency planning to ensure that access is maintained in and out of the City and throughout the Metro West region during hazard events. Focus on 1) facilitating emergency operations, 2) studying key junctions such as Exit 13, Exit 12, and the Route 9/126 intersection, and 3) considering approaches to improve and promote public transportation to help reduce cars on the road during inclement weather and reduce greenhouse gas emissions. | In Progress | Phase II of Transportation Master Plan completed in 2022. The City is also working on implementing public EV charging infrastructure to enourage residents to adopt electric vehicles. Implementation of a Downtown Parking Garage could support the community. | Fulfilled as part of 2022 Tranportation Plan?
Assess feasibility and funding options for property acquisitions along the Sudbury River and other flood-prone areas in the City with the intent of providing relief for property owners facing potential flood risks or repetitive losses and increasing available space for floodplain restoration to reduce flood impacts. | Delayed | Framingham is participating in an MVP Project titled the Sudbury-Assabet-Concord Natural Climate Solutions Grant that will support nature-based solutions. It is anticipated that this work could support the assessment of feasibility and funding options. | Why would properties need to be acquired? Shawn: According to the MVP report, areas downstream of dams on the Sudbury River would be threatened by floodwaters from a dam failure. Areas along the Sudbury River were noted as priority targets for improved riparian flood storage.
Coordinate with Framingham State University, MassBay Community College, and local community organizations to develop educational messaging and/or programming to transfer climate change risk and vulnerability knowledge to the general public, especially future generations. | Continuous | The City coordinates with Framingham State Unviersity (FSU) and Mass Bay Community College. For example, there is current coordination with Sustainability Coordinator and FSU on a student program to explore heat islands in Framingham. Coordination with local community organizations are in development. This measure is also supported by the MVP Climate Equity Project that Framingham is working on and will be further supported through the City's Climate Action Plan.
Lower Priority
Continue to support coordinated efforts to provide emergency shelters that effectively serve Framingham’s population during hazard events, including cooling and warming centers. Begin a City-wide discussion about informal sheltering to better understand how and when residents might use shelter services and redefine ‘sheltering’ to meet Framingham’s specific needs. For instance, if primary shelter use is for charging stations, develop locations where residents can meet this need during power outages without the expense of opening formal shelters. Consider how to support the use of informal sheltering locations where people already go in emergencies. | In Progress | The City continues to provide emergency shelters for heating and cooling during severe weather in summer and winter months. | Unrelated to this specific measure, plans were developed during COVID-19 for temprorary mortuaries, which can be important to preserving the capacity of critical resources such as emergency rooms at the local hospital in future emergencies.
Evaluate feasibility of City ordinance for private maintenance of problem trees. Such an ordinance can help increase utility resilience by reducing branch and tree falls during severe weather. | No Update | The City does not have an ordinance for the private maintenance of problem trees.
Explore and evaluate means of improving resiliency at historic properties throughout the City. | In Progress | Improvements to municipal historical buildings, such as the Old Edgell Library, are currently in progress through capital projects. It is possible that the the CPA may be able to provide additional support for local historic properties throughout the community.
Identify financial and technical assistance for MS4 implementation, to support municipal departments in complying with the MS4 permit. | Ongoing | Framingham has submitted by three annual reports for MS4 regarding BMPs. Annual reports detail technical assistance that Framingham has received to supprot MS4 implementation. The City is continually looking for financial assistance to support compliance with the MS4 permits. | Not appropriate for HMP, could likely be tied into another measure inthe plan.
Investigate potential for setting up and funding an emergency fund to support financially vulnerable populations during climate change related hazards and emergencies. This could include a surcharge on tax bills | Delayed | Framingham has implemented temproary financial assistance to families due to COVID-19, supporting many residents that are also highly vulnerable to climate change impacts. There are no current plans for a long-standing emergency fund covered by tax bills.
Collaborate with the state women’s prison, MCI-Framingham, to evaluate potential climate impacts related to hazard events such as flooding, drought and extreme heat. Assess resiliency of the prison facility. | Delayed | The State is currently evaluating the potential to replace MCI Framingham. All emergency plans of MCI-Framingham need to be approved by the Fire Chief annually. There is coordination with MCI Framingham on various issues. | Removed from cosnideration due to fact that future of prison is unclear.
Coordinate with MWRTA and MBTA to assess resiliency of commuter transportation, with particular focus on minimizing susceptibility to climate hazards and ensuring continued operations. Incorporate assessment of increased ridership and expanded offerings that would better connect employees with key business centers. | Continuous | The City has been engaged with MWRTA in several recent planning processes to identify opportunities to support public transportation options including the 2022 Transportation Master Plan. FD has maintained discussions with MWRTA for MWRTA to provide local transportation options in the event of an emergency.
Communicate with MEMA regarding the vulnerability of its command center and make efforts to increase the resiliency and safety of state emergency operations. | No Update / Remove | N/A
Facilitate education for prospective homebuyers and realtors to address flood risks to make sure that buyers are aware of what it means to purchase a home that may be located in or near a floodplain and educate residents on protections such as flood insurance that can mitigate financial risks associated with climate hazards. Target landlord associations and realtors to encourage risk communication. | Delayed | The City is currently evaluating opportunities to educate property owners about this issue.

## Updated HMP Actions & Priority
[5 empty] | Action Contextualization | [10 empty] | Action Prioritization
[16 empty] | High (Flood, Severe Winter Storms, Extreme Temperatures)= 3 Medium (Hurricanes/Wind, Thunderstorms, Drought, Infectious Disease)= 2 Low (Landslide, Wildfires, Tornadoes, Earthquakes, Invasive Species)= 1 | Low (Under $10k)= 3 Medium ($10k - $100k)= 2 High ($100k - $500k)= 1 Very High ($Over $500k)= 0 | Low Resource Commitment= 2 Medium Resource Commitment= 1 High Resource Commitment = 0 | 1-2 Years= 3 3-4 Years= 2 5 or More Years= 1 | Direct Support= 3 Indirect Support= 2 No Support= 0 | Major Support= 3 Moderate Support= 2 Minor Support= 1 None= 0 | Yes= 3 No= 0 | Yes= 2 No= 0 | Yes=2 No=0 | Large= 3 Medium= 2 Small= 1 Minor= 0 | Broad Support= 2 Moderate Support= 1 Unknown / Controversial = 0
[16 empty] | What level of hazards does the measure provide protection against? | How much will the measure cost to implement? | Does the measure require a signficant commitment of staff capacity or resources for operation and maintenance? | How long will it take for the measure to convey its benefits from the start of implementation efforts? | Does the measure provide support to Environmental Justice (EJ) and other Vulnerable Populations? | How effective is the measure directly in protecting lives and mitigating injuries resulting from the targeted hazard(s)? | Does the measure directly provide for the protection of critical facilities and infrastructure? | Does the measure protect natural resources? | Does the measure align with any of the HMP objectives? | How significant is the impact of this measure to the community in terms of its reach and the feasibility and weight of its impact? | Is there clear public support/ engagement of the community to implement and maintain the measure?
Primary Contact for Verification | Priority | For WG Meeting Review | Mitigation Measure | Type of Mitigation Action | Description | Status | Implementation Timeline | Responsible Department Lead | Supporting Agencies / Departments | Estimated Cost | Potential Funding Sources | Hazards Addressed | Critical Facility Protection (Y/N) | Source | Notes | Hazards Addressed | Approximate Cost | Internal Capacity | Implementation Timeline | Equity Focus | Protection of Lives | Protection of Critical Facilities or Infrastructure | Protection of Natural Resources | Alignment with Objectives | Anticipated Scale of Impact | Anticipated Public Support | Total Score
Robert Lewis | High | No | Complete rehabilitation of the Worcester Road Sewer Pump Station. | Structure & Infrastructure | The Worcester Road Pumping Station is Framingham's second-largest wastewater station, responsible for collecting and pumping sewage for over 4,000 homes and more than 200 businesses. The station provides service to approximately 25% of the city. Originally constructed in 1963, the station's equipment is outdated, does not meet current DPW standards, does not have a full backup power supply, and is at the end of its reliable service life. The pump station also does not meet current building codes, and the superstructure, including the roof, has structural deficiencies and will need replacement to extend the building’s life. Rehabilitation of the pump station will modernize the facility and ensure reliable operation in years ahead. | In Progress | 2027 | Director of Public Works | DPW | $$$$ (Over $5 million) | Capital Budget, MassDEP State Revolving Loan Program | Flooding | Y | Carried (HMP) |  | 3 | 0 | 1 | 2 | 3 | 3 | 3 | 3 | 2 | 3 | 1 | 24
Sarkis Sarkisian | High | Yes | Acquire the 103 Guild Street property. | Natural Resouces Protection | Acquire the 103 Guild Street property to secure valuable flood storage for the local neighborhood situated nearby Beaver Dam Brook. Property is located in an Environmental Justice Neighborhood. | In Progess | 2023 | Director of Planning, Conservation, and Community Development | Finance Department | $$$ (Negotiation Underway) | SVT, CPA Funding | Flooding | N | PCCD |  | 3 | 1 | 2 | 3 | 3 | 1 | 0 | 2 | 2 | 3 | 2 | 22
Sarkis Sarkisian | High | Yes | Acquire the CSX Corridor. | Natural Resouces Protection | Purchase of the 3.2 mile segment of the railway track will enable the City to add to the Bruce Freeman Rail Trail as well as protect vital stormwater capacity in the downtown area throughthe replacement of the CSX Hop Brook culvert. Acquisition of the property and subsequent improvements will help address problems related to historically undersized culverts and neighborhood flooding. | In Progress | 2023 | Director of Planning, Conservation, and Community Development | Finance Department (CFO), PCCD, DPW | $$$$ ($5 million) | Mass Trails Grant | Flooding | Y |  |  | 3 | 0 | 1 | 3 | 3 | 1 | 3 | 2 | 2 | 2 | 2 | 22
Robert Lewis | High | Yes | Retrofit, update, or replace undersized and unsafe culverts. | Structure & Infrastructure | Retrofit, update, or replace undersized and unsafe culverts to provide enhanced capacity to accomodate increased precipitation. Priority culverts include the Fuller Middle School Pedestrian Path Culvert, Edmands Road Culvert, and Colonial Drive Culvert. | In Progress | 2028 | Director of Public Works | Senior Stormwater & Environmental Engineer, DPW | $$$$ (Over $1.5 million) | Capital Budget; FEMA BRIC Grant; MA MVP Action Grants | Flooding | Y | Carried (HMP) |  | 3 | 0 | 0 | 1 | 3 | 3 | 3 | 2 | 2 | 3 | 2 | 22
Sarkis Sarkisian | High | Yes | Develop a Beaver Management Plan. | Local Plans & Regulations | Development of a plan to mitigate against unpredictable flooding/impoundment impacts. Establish creative engineering solutions, identify suitable areas for beaver relocation or where beaver activity may be creating flood storage that contributes to resiliency, and consider the development of special legislation to give the City authority to address problematic beaver dams on private property. Evaluate permitting feasibility of beaver deceivers or other non-lethal methods to mitigating the flood impact of problem beavers in flood-prone areas. | Uninitiated | 2026 | Director of Planning, Conservation, and Community Development | PCCD, Conservation Commission, Health Department | $$ ($10k < $100k) | Capital Budget; MVP Grant | Flooding, Severe Winter Storms | Y |  | Data source for cost: https://wbt.dot.state.fl.us/ois/TSMO/TrafficSignalBudgetingCostsAccessibleTables.htm, https://www.roadsbridges.com/safety/article/10644638/safety-2013-traffic-sunlights | 3 | 2 | 1 | 2 | 2 | 1 | 3 | 2 | 2 | 2 | 2 | 22
Sarkis Sarkisian | High | Yes | Protect or acquire private property impacted by flooding in repetitive loss neighborhoods and neighborhoods lacking infrastruture for future development. | Natural Resouces Protection | Protect or acquire private properties experiencing severe and repetitve flooding to reduce future disaste losses and provide important flood storage for surrounding neighborhoods. The acquisition and/or protection of properties would be prioritized in neighborhoods such as Hemenway Road, Auburn Street, Beaver Dam Brook, Prescott Street, Nixon Road, and the Circle Drive neighborhood as well as along the Subury River | In Progress | 2030 | Director of Planning, Conservation, and Community Development | DPW | $$$$ (Over $1 million) | Capital Budget, MVP Action Grant | Flooding | Y | Carried (HMP) |  | 3 | 0 | 1 | 1 | 3 | 3 | 3 | 2 | 2 | 3 | 1 | 22
Shawn Luz | High | No | Integrate relevant hazard mitigation plan priorities and actions into the City's forthcoming Climate Action Plan. | Local Plans & Regulations | Integrate relevant HMP priorities and actions into the development of the City's Climate Action Plan (2023). Development of the City's first Climate Action Plan will be underway in October 2022 and coordination with relevant items from the HMP plan will ensure expedient progress toward goals and generally support efforts to improve the resiliency of the community. | New | 2023 | Sustainability Coordinator | Sustainability Committee, MAPC | $ (Staff Time Commitment) | Capital Budget, MAPC Technical Assistance, Executive Office of Energy and Environmental Affiars (EOEEA) Planning Assistance Grant | Extreme Temperatures, Flooding, Severe Winter Storms, Drought, Tornadoes, Hurricanes | N | Sustainability Coordinator |  | 3 | 3 | 2 | 3 | 3 | 0 | 0 | 2 | 2 | 1 | 2 | 21
Sarkis Sarkisian | High | Yes | Protect and restore wetland areas and water bodies. | Natural Resouces Protection | Complete wetlands construction projects and ecological restorations of existing wetlands to improve flood storage capacity and water quality. Coordinate regionally to reduce pesticide and nutrient inputs from stormwater runoff through public engagement and education. A priority area includes the City's conditions assessment and potential wetlands restoration to improve water quality at the Lake Waushakum outfall as well as regional coordination on the management of Lake Cochituate. | In Progress | 2026 | Director of Planning, Conservation, and Community Development | PCCD, DPW | $$$ (Lake Waushakum Infrastructure and Water Quality Improvements $600k) | Capital Budget (ARPA), Regional MVP Action Grant | Flooding, Severe Winter Weather, Invasive Species | N | Carried (HMP) |  | 3 | 1 | 2 | 2 | 3 | 1 | 0 | 2 | 2 | 3 | 2 | 21
Shawn Luz | High | No | Evaluate and pursue opportunities to use clean energy technologies, such as microgrids, to provide enhanced backup power to municipal facilities. | Structure & Infrastructure | Explore the implementation of solar PV, battery storage, and other renewable energy technologies to provide clean energy resilience to critical municipal facilities as part of efforts to epand renewable energy technologies | In Progress | 2025 | Sustainability Coordinator | Capital Projects and Facilities Management, DPW, Framingham Public Schools | $$$ (>$100k) | MassCEC CLEAR Grant, Capital Budget | Severe Winter Storms, Flooding, Extreme Temperatures, Hurricanes, Thunderstorms | Y |  |  | 3 | 1 | 1 | 2 | 3 | 2 | 3 | 0 | 2 | 2 | 2 | 21
Robert Lewis | High | Yes | Adopt, implement, and maintain a Comprehensive Flood Hazard Mitigation Plan. | Local Plans & Regulations | A requirement for the CRS Program for all repetitive loss communities, utilize standard planning process to develop a Comprehensive Flood Hazard Mitigation Plan for the City. To ensure cotninued value to the community and compliance with CRS Program requirements, updates to the plan would be required every 5 years. | New | 2027 | Director of Public Works | DPW | $$ ($50k) | N/A | Flooding | Y | Carried (HMP) |  | 3 | 2 | 0 | 2 | 2 | 1 | 3 | 2 | 2 | 2 | 2 | 21
James Snyder | High | No | Improve flood storage at Mary Dennison Park. | Natural Resouces Protection | Utilize the redesign of the Mary Dennision Park as an opportunity to preserve existing flood storage capacity located at the back of the facility. Protection of this flood storage will improve the resilience of local infrastructure and community facilities, such as adjacent affordable housing, to flooding. | New | 2026 | Director of Parks and Recreation | Mass DEP; DPW | $$$$ ($20 - $25 million) | Mary Dennison Settlement and Town Meeting / Capital Budget | Flooding | Y | PCCD |  | 3 | 0 | 2 | 2 | 3 | 2 | 3 | 0 | 2 | 2 | 2 | 21
Robert Lewis | High | Yes | Implement flood mitigation measures in the Walnut Street neighborhood. | Natural Resouces Protection | Develop and implement design and permitting for wetland, stream channel, and streambank restorations to reduce flooding and increase brook capacity in the Walnut Street/Sucker Brook Drainage Area. | In Progress | 2025 | Director of Public Works | MVP | $$$$ ($2 - 2.5 million) | MVP Grant | Flooding | N | DPW |  | 3 | 0 | 1 | 2 | 3 | 3 | 0 | 2 | 2 | 3 | 2 | 21
Chief Dutcher | High | No | Continue to support coordinated efforts to provide emergency shelters and evaluate the specific needs for enhanced capacity in areas of the community. | Structure & Infrastructure | Provide shelters that that effectively serve Framingham’s population during hazard events, including cooling and warming centers such as the Framingham Public Library branches and the Callahan Senior Center. Evaluate the necessity of locations over time to support vulnerable populations. | In Progress | 2023 | Director of Emergency Management | DPW, CPFM, FPS | $ (Under $10k) | Operating Budget | Extreme Temperatures, Flooding, Severe Weather, Drought, Infectious Disease, Wildfires, Tornadoes, Earthquakes, Hurricanes | N |  |  | 3 | 3 | 1 | 3 | 3 | 3 | 0 | 0 | 2 | 1 | 2 | 21
Robert Lewis | High | Yes | Facilitate education for prospective homebuyers and realtors to address flood risks. | Outreach & Education | Provide education to make sure that buyers are aware of what it means to purchase a home that may be located in or near a floodplain and educate residents on protections such as flood insurance that can mitigate financial risks associated with climate hazards. Target landlord associations and realtors to encourage risk communication. | Uninitiated | 2023 | Director of Public Works | DPW, Sustainability Coordinator, PCCD | $ (Under $10k) | Operating Budget | Flooding | N |  |  | 3 | 3 | 2 | 3 | 2 | 1 | 0 | 2 | 2 | 2 | 1 | 21
Robert Lewis | High | Yes | Develop a Comprehensive Stormwater Master Plan. | Local Plans & Regulations | The Comprehensive Stormwater Master Plan will complete Phases IV and V of the City's study of the stromwater system which involve the study of ten sub-basins: North and South Saxonville, Cherry Meadow Brook, Birch Meadow Brook, Baiting Brook, Wayside, Square Meadow Brook, Reservoir #1 and #2 South, Reservoir #3 North, and Willow Brook drainage sub-basins. It will also include updated analysis off flooding along Beaver Dam Brook. | In Progress | 2028 | Director of Public Works | DPW | $$$ ($950k) | Capital Budget | Flooding, Severe Winter Storms | Y | Carried (HMP) |  | 3 | 1 | 1 | 1 | 2 | 1 | 3 | 2 | 2 | 3 | 2 | 21
Shawn Luz | High | No | Utilize clean energy technologies to provide efficient heating and cooling capacity to municpal facilities and schools. | Structure & Infrastructure | Implement heat pump systems to provide efficient relief to occupants of municipal facilities and schools from rising summer temperatures while enhancing efficiency of/and reducing reliance on natural gas-fired winter heating systems. Schools currently without full air conditioning solutions include Brophy Elementary School, Dunning Elementary School, Hemenway Elementary School, McCarthy Elementary School, Potter Road Elementary School, Stapleton Elementary School, and Walsh Middle School. | In Progress | 2027 | Sustainability Coordinator | Framingham Public Schools; CPFM; DPW | $$$$ (Over $20 million) | Eversource, Green Communities Competitive Grants, Capital Budget, ARPA | Extreme Temperatures | Y |  |  | 3 | 0 | 1 | 2 | 3 | 2 | 3 | 0 | 2 | 3 | 2 | 21
Robert Lewis | High | No | Replace the School Street, Taralli Terrace, Potter Road, and Second Street Bridges. | Structure & Infrastructure | Replace outdated bridges and associated infrastructure that serve as critical links in the City's transportation network. Priority bridges for replacement include the School Street Bridge over Cochituate Brooks as well as the Taralli and Second Street Bridges where flooding has occured in the past. Potter Road Bridge is also in need of replacement. Replacement of these bridges will better ensure their operational status in the event of a critical natural hazard. | In Progress | 2027 | Director of Public Works | Senior Stormwater & Environmental Engineer, DPW | $$$$ (Taralli and Second Street Bridge Replacement Evaluations: $200k, School Street Bridge Design and Construction: $500k) | Capital Budget | Flooding, Severe Winter Storms, Hurricanes, Tornadoes, Earthquakes | Y | Carried (HMP) |  | 3 | 0 | 0 | 2 | 3 | 3 | 3 | 0 | 2 | 3 | 2 | 21
Shawn Luz | Medium | No | Coordinate local community organizations to develop educational messaging and/or programming to transfer climate change risk and vulnerability knowledge to the general public. | Outreach & Education | Communicate with Framingham State University, Mass Bay Community College, and other local organizations to increase awareness of climate change risks. | In Progress | 2024 | Sustainability Coordinator | PCCD, DPW, Sustainability Committee | $ (Under $10k) | Operating Budget; MAPC Technical Assistance | Extreme Temperatures, Flooding, Severe Weather, Drought, Infectious Disease, Wildfires, Tornadoes, Earthquakes, Hurricanes | N |  |  | 3 | 3 | 2 | 3 | 3 | 1 | 0 | 0 | 2 | 1 | 2 | 20
Robert Lewis | Medium | Yes | Develop green infratructure on municipal properties to improve stormwater management and reduce heat island impacts. | Structure & Infrastructure | Assess drainage infrastructure and drainage-driven road flooding and develop green infrastructure solutions for stormwater management and urban heat island mitigation to be used in tandem with improvements to the outdated and undersized stormwater system to reduce road flooding and problems with ice slicks that make roads dangerous or impassable during hazard events. Develop a list of specific priorities, assess feasibility and cost, rank priority projects in terms of climate resilience potential, and develop concept designs for key projects. Projects in areas of the community with high proportions of impermeable surface area, such as downtown Framingham, shall be prioritized as well as facilities such as Butterworth park. | In Progress | 2029 | Director of Public Works | DPW, Sustainability Coordinator | $$$ ($100k - $500k) | Capital Budget, MVP Action Grant, DCR Urban Forestry Challenge Grant | Flooding, Wildfires, Extreme Temperatures | Y | Carried (HMP) MVP Overlap |  | 3 | 1 | 2 | 1 | 2 | 1 | 3 | 3 | 2 | 1 | 1 | 20
Robert Lewis | Medium | No | Assess City-owned dams and engage other public and private dam owners in Framingham on resilience. | Outreach & Education | Evaluate the condition of two public dams owned by the City: the Landham Pond Dam and the Mt. Wayte Outlet Works. Coordinate with other public and private dam owners, such as Massachusetts Water Resources Authority (MWRA) and Massachusetts Department of Conservation and Recreation (DCR) and DCR to help support the health and resilience of this infrastructure. | Uninitiated | 2025 | Director of Public Works | DPW, United States Army Corps of Engineers, Private Dam Owners, PCCD | $$ ($10k < $100k) | Operating Budget; Administrative Resources | Flooding, Severe Winter Storms, Hurricanes, Tornadoes, Earthquakes | Y |  |  | 3 | 2 | 1 | 2 | 2 | 1 | 3 | 2 | 2 | 1 | 1 | 20
Chief Dutcher | Medium | Yes | Plan and post neighborhood and regional evacuation routes. | Outreach & Education | Develop and publicize neighborhood and regional evacuation routes to support the safe evacuation of Framingham residents, with emphasis on vulnerable populations. | Uninitiated | 2024 | Director of Emergency Management | EMA, Police Departmnet, DPW, MEMA | $$ ($10k < $100k) | Operating Budget | Extreme Temperatures, Flooding, Severe Weather, Tornadoes, Earthquakes, Hurricanes | N |  |  | 3 | 2 | 1 | 3 | 2 | 3 | 0 | 0 | 2 | 2 | 2 | 20
Robert Lewis | Medium | Yes | Purchase & install automated weather stations and additional pavement sensors. | Structure & Infrastructure | Purchase and install 4 automated weather stations throughout the City, with web-based access. Weather stations will assist DPW personnel with assessing storms to improve response to extreme precipitation, high winds, and winter storms. They will also assist the Police Deprtment & Fire Department with emergency response for storm events. Additionally, the DPW Highway Department use pavement sensors to evaluate the temperature of pavement during cold weather. Installation of additional sensors will enhance the Highway Department's ability to identify roads for pretreatment which reduces roadway icing and other hazards associated with winter storms. | N/A | 2027 | Director of Public Works | Department of Public Works, Police Department, Fire Department | $$ ($10k < $100k) | Operating Budget; FEMA BRIC Grant | Extreme Temperatures, Flooding, Severe Winter Storms, Drought | Y | Carried (HMP) |  | 3 | 2 | 1 | 2 | 2 | 2 | 3 | 0 | 2 | 2 | 1 | 20
James Paolini | Medium |  | Assess at a high level flood-proofing measures and flood storage to prevent future flooding at the Callahan Senior Center. | Structure & Infrastructure | Explore additional opportunities to improve flood storage following the installation of floodproofing at the Callahan Senior Center. |  | 2027 | Director of Capital Projects and Facilities Management | DPW | $ (Staff Time Commitment) | Operting Budget | Flooding | Y |  |  | 3 | 3 | 1 | 2 | 3 | 2 | 3 | 0 | 2 | 0 | 1 | 20
Shawn Luz | Medium | Yes | Develop and implement a municipal program to promote the use of green infrastructure to the business community. | Outreach & Education | Develop a green infrastructure marketing/education campaign focusing on businesses and large commerical developments to help mitigate stormwater runoff and the heat island effect, particularly in areas of downtown Framingham with high levels of immereable surface and flooding risks. This program would support requirements of the City's NPDES MS4 permit. | In Progress | 2024 | Sustainability Coordinator | PCCD, DPW, Sustainability Coordinator | $ ($10k) | MAPC Accelerating Climate Resilience (ACR) Grant Program | Flooding, Extreme Temperatures, Invasive Species | N | Carried (HMP) |  | 3 | 3 | 1 | 3 | 2 | 1 | 0 | 2 | 2 | 2 | 1 | 20
Shawn Luz | Medium | No | Foster an improved communications network to better reach vulnerable populations and those most in need of information and assistance. | Outreach & Education | Identify vulnerable populations and foster an improved communications network in advance of hazard events to facilitate communication efforts and outreach to those most in need of information and assistance. Expand upon current efforts to strengthen relationships with Framingham's Environmental Justice neighborhoods. | In Progress | 2024 | Sustainability Coordinator | Emergency Management Agency | $$ ($10k < $100k) | Operating Budget; MAPC Technical Assistance | Extreme Temperatures, Flooding, Severe Winter Stormsr, Drought, Wildfires, Tornadoes, Earthquakes | N |  |  | 3 | 2 | 1 | 3 | 3 | 2 | 0 | 0 | 2 | 2 | 2 | 20
Robert Lewis | Medium | Yes | Implement draingage improvements to support transportation networks and associated properties. | Structure & Infrastructure | Implement drainage improvements along roadways that reduce flooding and improve the resilience of transportation infrastructure. Priority areas for the implementation of drainage improvements include Fountain Street (currently undergoing a comprehensive capital project that includes drainage improvements and replacement of the Farm Pond Outfall) and the Nobscott Area (for which drainage improvements are being implemented through development of the Nobscott Plaza). | In Progress | 2026 | Director of Public Works | Senior Stormwater & Environmental Engineer, DPW | $$$$ (Over $500k) | Capital Budget | Flooding, Severe Winter Weather | Y | Carried (HMP) |  | 3 | 0 | 1 | 2 | 2 | 2 | 3 | 0 | 2 | 3 | 2 | 20
Sarkis Sarkisian | Medium | Yes | Develop standards to prioritize social equity in resilience project planning, design, and development. | Outreach & Education | Develop standards by which municipal departments can prioritize the equitable share of benefits from hazard mitigation actions to support Environmental Justice (EJ) and vulnerable populations in the community. | New | 2025 | Director of Planning, Conservation, and Community Development | Sustainability Coordinator | $ (Staff Time and HUD Technical Assistance) | U.S. Department of Housing and Urban Development Technical Assistance, CBDG funds | Extreme Temperatures, Flooding, Severe Weather, Drought, Infectious Disease, Wildfires, Tornadoes, Earthquakes, Hurricanes | N | CBDG |  | 3 | 3 | 2 | 2 | 3 | 1 | 0 | 0 | 2 | 2 | 1 | 19
Sarkis Sarkisian | Medium | Yes | Integrate flood storage review into Open Space Plan. | Local Plans & Regulations | Integrate flood storage capacity as a criterion in the City's Open Space Plan's priority list of open space parcels to protect from future development. Inclusion of this information in the analysis will help the City more clearly identify properties that would be prime candidates for increasing flood storage and mitigate flooding impacts. | N/A | 2023 | Director of Planning, Conservation, and Community Development | Senior Stormwater & Environmental Engineer, Parks & Recreation Director | $ (Staff Time Commitment, Technical Assistance) | Operating Budget | Flooding | N | Carried (HMP) |  | 3 | 3 | 1 | 3 | 2 | 1 | 0 | 2 | 2 | 1 | 1 | 19
Shawn Luz | Medium | No | Partner with the local utility on climate resilience efforts. | Outreach & Education | Enhance coordination to identify and address vulnerabilities in utility infrastructure and enhance communication and cooperation between the City and private utilities. | In Progress | 2023 | Sustainability Coordinator | DPW, CPFM, Schools | $ (Under $10k) | Operating Budget | Extreme Temperatures, Flooding, Severe Winter Weather | N |  |  | 3 | 3 | 2 | 3 | 2 | 2 | 0 | 0 | 2 | 1 | 1 | 19
Robert Lewis | Medium | Yes | Coordinate regional management efforts of Lake Cochituate. | Outreach & Education | Work with state agencies and neighboring communities such as Towns of Natick and Wayland to reduce pesticide and nutrient inputs from stormwater runoff through public engagement and education. | In Progress | 2024 | Director of Public Works | Mass DCR, Town of Natick, Town of Wayland | $ ($10k < $100k) | Regional MA MVP Action Grant | Extreme Temperatures, Invasive Species, Infectious Disease | N |  |  | 3 | 3 | 2 | 3 | 2 | 0 | 0 | 2 | 2 | 1 | 1 | 19
Robert Lewis | Medium | Yes | Evaluate and enhance current ordinances and regulations regarding floodplain development. | Local Plans & Regulations | Review zoning ordinances, planning and wetlands regulations, building code, as well as health and safety regulations to ensure consistency across regulations and the collaborative mitigation of risks, such as avoiding development in floodplains. | N/A | 2026 | Director of Public Works | PCCD, Planning Board, Conservation Commission | $$ ($25k < $50k?) | Capital Budget | Flooding, Severe Winter Storms | N | Carried (HMP) |  | 3 | 2 | 1 | 2 | 2 | 2 | 0 | 2 | 2 | 3 | 0 | 19
Shawn Luz | Medium | No | Continue community engagement efforts to maximize the adoption of energy efficiency and clean energy technologies at new and existing buildings. | Outreach & Education | Improve the resilience of local buildings to extreme weather conditions through community engagement focused on advancing clean energy and energy efficiency development in new and existing buildings. Community engagement should leverage and coordinate technical and financial resources from the utility, state, and other entities, such as the Mass Save Program, to empower residents and businesses to implement energy efficiency improvements and install clean energy systems. The intensification of climate change impacts threatens critical local infrastructure including the electrical grid and powered devices. Energy efficient, well-insulated buildings can maintain habitable conditions for longer durations in the event of prolonged utility outages that may be caused by flooding, severe weather, and extreme heat. Enhanced local energy efficiency can also reduce stress on the local electrical grid during periods of peak demand, increasing system reliability for nearby facilities. | In Progress | 2024 | Sustainability Coordinator | Mass Save, Eversource, Town of Natick | $$ ($100,000) | Mass Save (Eversource), U.S. Department of Housing and Urban Development Technical Assistance | Flooding, Severe Winter Storms, Extreme Temperatures, Hurricanes, Tornadoes, Thunderstorms, Earthquakes | N | Carried (MVP) |  | 3 | 2 | 1 | 3 | 3 | 1 | 0 | 0 | 2 | 2 | 2 | 19
Robert Lewis | Medium | Yes | Install additional stream gauges and web-based public portal for stream gauge data. | Structure & Infrastructure | Install additional automated stream gauges (surface water level sensors and communications equipment) at high risk areas, including Angelica Drive (Angelica Brook) Bates Rd (Beaver Dam Brook). | N/A | 2027 | Director of Public Works | DPW | $$$ ($15,000-$30,000/each) | Capital Budget; FEMA BRIC Grant | Flooding, Drought | Y | Carried (HMP) |  | 3 | 1 | 1 | 2 | 2 | 2 | 3 | 0 | 2 | 2 | 1 | 19
Robert Lewis | Medium | No | Implement recommendations from the feasibility study for removal of the Landham Pond Dam. | Structure & Infrastructure | Implement flood and drainage mitigation measures in the Hemenway neighborhood associated with the removal of the Landham Pond Dam. The implementation of these measures is contingent on the acquisition of the CSX property associated with the Bruce Freeman Rail Trail. | Uninitiated | 2029 | Director of Public Works | PCCD, DPW | $$$$ (Over $2 million) | FEMA BRIC Grant, Capital Budget | Flooding, Severe Winter Storms | N |  |  | 3 | 0 | 1 | 1 | 2 | 2 | 0 | 3 | 2 | 3 | 1 | 18
Robert Lewis | Medium | No | Implement emergency generators for traffic signals. | Structure & Infrastructure | Implement emergency backup power generation (such as solar PV and batteries) to power traffic signals in the event of power disruptions due to natural hazards (such as severe storms) and hazard-related events. For example, during a 2013 storm event, power was lost at a major intersection's traffic signal for 6 days. Police details were required, pulling limited emergency personnel from other weather-related emergencies. Loss of power to traffic signals compounds hazardous travel conditions. Emergency, back-up generators for traffic signals will help facilitate traffic flow and mitigate hazardous conditions. | New | 2028 | Director of Public Works | DPW | $$$ ($350k, estimated to be between $7k each with 50 signalized intersections) | Capital Budget | Severe Winter Storms, Flooding, Extreme Temperatures, Hurricanes, Thunderstorms | Y | Carried (HMP) |  | 3 | 1 | 1 | 1 | 2 | 2 | 3 | 0 | 2 | 2 | 1 | 18
Shawn Luz | Low | No | Conduct a power quality and surge protection study of critical municipal facilities. | Local Plans & Regulations | Conduct an analysis of critical municipal facilities for vulnerabilities and power quality needs to ensure the long-term reliability of electronics and other building-connected electrical equipment in an emergency situation such as a prolonged climatic hazard. The intensification of climate change impacts threatens critical local infrastructure including the electrical grid and powered devices. Disruptions to the electrical grid caused by outages (severe winds, snowstorms, flooding) and brownouts (stemming from excessive demand during extreme weather) can severly damage connected equipment and reduce or delay the ability of critical facilities to support the public. | New | 2026 | Sustainability Coordinator | Eversource | $$ ($50,000) | Capital Budget | Extreme Temperatures, Severe Winter Storms, Thunderstorms | Y | Sustainability Coordinator |  | 3 | 2 | 1 | 2 | 2 | 1 | 3 | 0 | 2 | 1 | 0 | 17
Robert Lewis | Low | No | Develop a citywide comprehensive tree and forest management program. | Local Plans & Regulations | Development of a plan to identify, remove, and replace problem trees, preserve intact forests and street tree cover, provide guidance and resources for gradually moving toward more climate-resilient trees and forest communities (e.g. species that will tolerate warmer temperatures) and develop guidelines to manage conversion of forest land and require shade tree plantings in new developments to promote erosion control and improved infiltration. | Uninitiated | 2025 | Director of Public Works | DPW, Sustainability Coordinator, PCCD | $$ ($10k < $100k) | DCR Ubran Forestry Grant; MAPC Acclerating Climate Resiliency Grant; Capital Budget | Flooding, Severe Winter Storms, Extreme Temperatures | N |  |  | 3 | 2 | 0 | 2 | 2 | 1 | 0 | 2 | 2 | 2 | 1 | 17
Sarkis Sarkisian | Low |  | Explore the development of a Hazard Mitigation Incentive Program. | Local Plans & Regulations | Explore options for incentives which may include zoning amendments to encourage property owners to engage in mitigation. | Uninitiated | 2028 | Director of Planning, Conservation, and Community Development | DPW, Conservation Commission | $ (Operating Budget) | CPA Funding | Flooding, Severe Winter Storms, Extreme Temperatures, Hurricanes, Drought, Tornadoes | N |  |  | 3 | 3 | 0 | 1 | 2 | 1 | 0 | 3 | 2 | 2 | 0 | 17
Robin Williams | Low |  | Assess additional mosquito/pest control options, including increased stormwater BMP maintenance. | Outreach & Education | Determine future risks due to increase in type and quantity of pests/disease vectors due to climate change and develop education and outreach efforts as well as strategies to improve resilience. |  | 2029 | Director of Health Department | DPW | $$ ($10k < $100k) | Operating Budget | Invasive Species, Infectious Disease | N |  |  | 2 | 2 | 0 | 1 | 2 | 1 | 0 | 3 | 2 | 2 | 1 | 16
Robert Lewis | Low | No | Evaluate satellite locations to supplement DPW operations center and salt storage. | Local Plans & Regulations | Evaluate an alternative location for salt strorage that is currently located at the Henry Street Garage in order to provide better support citywide and reduce response times during severe winter weather and storms. | In Progress | 2030 | Director of Public Works | DPW | $$ ($10k < $100k) | Operating Budget | Flooding, Severe Winter Storms, Hurricanes, Tornadoes, Earthquakes | Y |  |  | 3 | 2 | 1 | 1 | 2 | 1 | 3 | 0 | 2 | 1 | 0 | 16
Sarkis Sarkisian | Low | Yes | Develop a citywide Business Resilience Plan. | Local Plans & Regulations | Develop plan to support local businesses and make the business community more resilient. Identify business development areas where impacts from climate hazards can be easily avoided or mitigated (e.g., by avoiding floodplains or areas of known drainage-related flooding) and targeted improvements, such as a microgrid and rooftop solar installations, employed to provide extra resilience to community businesses in the Downtown and I-90 Exits 12 and 13 areas. | Uninitiated | 2027 | Director of Planning, Conservation, and Community Development | Sustainability Coordinator | $$ ($10k < $100k) | Capital Budget | Extreme Temperatures, Flooding, Severe Winter Storms, Hurricanes, Infectious/Disease Drought | N |  |  | 3 | 2 | 1 | 2 | 2 | 1 | 0 | 0 | 2 | 2 | 1 | 16
Robert Lewis | Low | Yes | Conduct robust transportation resiliency planning. | Local Plans & Regulations | Develop a plan or amendment to 2022 Transportation Master Plan to help safeguard transportation during natural hazard events with emphasis on facilitating emergency operations and ensure that access is maintained in and out of the City and throughout the MetroWest region during hazard events. The plan will study key junctions such as Exit 13, Exit 12, and the Route 9/126 intersection. Development of the plan will require coordination with the MWRTA and MBTA to assess the resiliency of commuter transportation. | Uninitiated | 2028 | Director of Public Works | Emergency Management Agency, MWRTA, MBTA, Sustainability Coordinator | $$ ($10k < $100k) | Operating Budget; EEA Planning Assistnace Grant | Extreme Temperatures, Flooding, Severe Winter Storms, Hurricanes, Infectious/Disease Drought | N |  |  | 3 | 2 | 0 | 1 | 2 | 2 | 0 | 0 | 3 | 2 | 1 | 16
Robert Lewis | Low | Yes | Reimplement residential rain barrel program. | Outreach & Education | Reimplement a residential rain barrel program to offer discounted rain barrels to help improve stormwater management, reducing the risk of flooding as well as enabling residents to mitgate the impact of droughts. | New | 2023 | Director of Public Works | Sustainability Coordinator | $ (Under $10k) | MassDEP Sustainable Materials Recovery Program (SMRP) | Flooding, Drought | N | Carried (HMP) |  | 3 | 3 | 2 | 3 | 0 | 0 | 0 | 0 | 2 | 1 | 2 | 16
Robert Lewis | Low | No | Conduct a community engagement campaign on water conservation. | Outreach & Education | Expand water conservation efforts for Framingham residents and businesses to mitigate consumption of MWRA and local well water to improve local resiliency to droguht conditions. | Uninitiated | 2023 | Director of Public Works | Massachusetts Water Resource Authroity (MWRA), Sustainability Coordinator | $$ ($10k < $100k) | Operating Budget | Drought | N |  |  | 2 | 2 | 2 | 3 | 2 | 0 | 0 | 2 | 2 | 0 | 1 | 16
Robert Lewis | Low | No | Explore intermunicipal connections with neighboring communities for water resources. | Local Plans & Regulations | Explore the potential for intermunicipal connections with other communities to access water resoruces that can safeguard against potential regional capacity risks through the MWRA in times of drought. This would include a high-level analysis of the major logistical, regulatory, financial, and health challenges involved with intermunicipal connnection. | Uninitiated | 2025 | Director of Public Works | DPW, PCCD, MWRA | $$ ($10k < $100k) | Capital Budget | Drought, Invasive Species | N |  |  | 3 | 2 | 0 | 2 | 2 | 2 | 0 | 0 | 2 | 0 | 0 | 13
Shawn Luz | Low | Yes | Explore and evaluate means of improving resiliency at historic properties. | Structure & Infrastructure | Identify opportunities to improve the resilience of municipal and private historical facilities throughout the community to climate change impacts such as extreme heat, severe weather, and flooding. | In Progress | 2028 | Sustainability Coordinator | PCCD, Framingham Historical Society, CPFM, Community Preservation Committee | $$ ($10k < $100k) | Operating Budget | Flooding, Severe Winter Storms, Extreme Temperatures, Hurricanes, Tornadoes | N |  |  | 3 | 2 | 2 | 1 | 0 | 1 | 0 | 0 | 2 | 0 | 1 | 12
Note on Y3: Shawn M. Luz: • Infrastructure: Mitigate risk to critical facilities and infrastructure from natural hazards and climate change. • Capacity: Expand the City's capacity to mitigate risk by adopting a culture of hazard mitigation through regulations, planning, and regional collaboration. • Natural Resources: Implement actions that minimize risk from climate change and natural hazards to preserve or restore the functions of natural systems. • Education: Educate all stakeholders about the value of hazard mitigation and how to implement it in their work, businesses, and homes.

## Action Analysis (hidden)
Count of Mitigation Measure | Column Labels
Row Labels | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030 | Grand Total
Chief Engineer |  |  |  | 1 | 1 |  | 1 |  | 3
Community Development Coordinator |  |  | 1 | [5 empty] | 1
Department of Public Works Director | 2 |  | 1 |  | 2 | 2 | 1 | 1 | 9
Director of Capital Projects and Facilities Management |  |  |  |  | 1 |  |  |  | 1
Director of Emergency Management |  | 1 | [6 empty] | 1
Director of Health Department | [6 empty] | 1 |  | 1
Director of Highway and Sanitation | [5 empty] | 1 |  |  | 1
Director of Parks and Recreation |  |  |  | 1 |  |  |  |  | 1
Director of Planning, Conservation, and Community Development | 1 | 1 | 1 | 2 | 1 | 1 |  | 1 | 8
Director of Water & Wastewater |  |  | 1 |  | 1 |  |  |  | 2
Emergency Management Director | 1 | [7 empty] | 1
Senior Stormwater & Environmental Engineer | 1 | 2 | 1 | 1 | 1 | 1 |  |  | 7
Sustainability Coordinator | 2 | 3 | 1 | 1 | 1 | 1 |  |  | 9
Tree Warden |  |  | 1 | [5 empty] | 1
Grand Total | 7 | 7 | 7 | 6 | 8 | 6 | 3 | 2 | 46

## Ordered Updated HMP List (hidden)
Priority | Hazard Mitigation Action | Category
High | Complete rehabilitation of the Worcester Road Sewer Pump Station. | Structure & Infrastructure
High | Acquire the 103 Guild Street property. | Natural Resouces Protection
High | Acquire the CSX Corridor. | Natural Resouces Protection
High | Retrofit, update, or replace undersized and unsafe culverts. | Structure & Infrastructure
High | Develop a Beaver Management Plan. | Local Plans & Regulations
High | Protect or acquire private property impacted by flooding in repetitive loss neighborhoods and neighborhoods lacking infrastruture for future development. | Natural Resouces Protection
High | Integrate relevant hazard mitigation plan priorities and actions into the City's forthcoming Climate Action Plan. | Local Plans & Regulations
High | Protect and restore wetland areas and water bodies. | Natural Resouces Protection
High | Evaluate and pursue opportunities to use clean energy technologies, such as microgrids, to provide enhanced backup power to municipal facilities. | Structure & Infrastructure
High | Adopt, implement, and maintain a Comprehensive Flood Hazard Mitigation Plan. | Local Plans & Regulations
High | Improve flood storage at Mary Dennison Park. | Natural Resouces Protection
High | Implement flood mitigation measures in the Walnut Street neighborhood. | Natural Resouces Protection
High | Continue to support coordinated efforts to provide emergency shelters and evaluate the specific needs for enhanced capacity in areas of the community. | Structure & Infrastructure
High | Facilitate education for prospective homebuyers and realtors to address flood risks. | Outreach & Education
High | Develop a Comprehensive Stormwater Master Plan. | Local Plans & Regulations
High | Utilize clean energy technologies to provide efficient heating and cooling capacity to municpal facilities and schools. | Structure & Infrastructure
High | Replace the School Street, Taralli Terrace, Potter Road, and Second Street Bridges. | Structure & Infrastructure
Medium | Coordinate local community organizations to develop educational messaging and/or programming to transfer climate change risk and vulnerability knowledge to the general public. | Outreach & Education
Medium | Develop green infratructure on municipal properties to improve stormwater management and reduce heat island impacts. | Structure & Infrastructure
Medium | Assess City-owned dams and engage other public and private dam owners in Framingham on resilience. | Outreach & Education
Medium | Plan and post neighborhood and regional evacuation routes. | Outreach & Education
Medium | Purchase & install automated weather stations and additional pavement sensors. | Structure & Infrastructure
Medium | Assess at a high level flood-proofing measures and flood storage to prevent future flooding at the Callahan Senior Center. | Structure & Infrastructure
Medium | Develop and implement a municipal program to promote the use of green infrastructure to the business community. | Outreach & Education
Medium | Foster an improved communications network to better reach vulnerable populations and those most in need of information and assistance. | Outreach & Education
Medium | Implement draingage improvements to support transportation networks and associated properties. | Structure & Infrastructure
Medium | Develop standards to prioritize social equity in resilience project planning, design, and development. | Outreach & Education
Medium | Integrate flood storage review into Open Space Plan. | Local Plans & Regulations
Medium | Partner with the local utility on climate resilience efforts. | Outreach & Education
Medium | Coordinate regional management efforts of Lake Cochituate. | Outreach & Education
Medium | Evaluate and enhance current ordinances and regulations regarding floodplain development. | Local Plans & Regulations
Medium | Continue community engagement efforts to maximize the adoption of energy efficiency and clean energy technologies at new and existing buildings. | Outreach & Education
Medium | Install additional stream gauges and web-based public portal for stream gauge data. | Structure & Infrastructure
Medium | Implement recommendations from the feasibility study for removal of the Landham Pond Dam. | Structure & Infrastructure
Medium | Implement emergency generators for traffic signals. | Structure & Infrastructure
Low | Conduct a power quality and surge protection study of critical municipal facilities. | Local Plans & Regulations
Low | Develop a citywide comprehensive tree and forest management program. | Local Plans & Regulations
Low | Explore the development of a Hazard Mitigation Incentive Program. | Local Plans & Regulations
Low | Assess additional mosquito/pest control options, including increased stormwater BMP maintenance. | Outreach & Education
Low | Evaluate satellite locations to supplement DPW operations center and salt storage. | Local Plans & Regulations
Low | Develop a citywide Business Resilience Plan. | Local Plans & Regulations
Low | Conduct robust transportation resiliency planning. | Local Plans & Regulations
Low | Reimplement residential rain barrel program. | Outreach & Education
Note on B25: Shawn M. Luz: Combine with automated weather sensors?

## Additional Recommendations V2 (hidden)
Priority | Mitigation Measure | Type of Mitigation Action | Description | Status | Implementation Timeline | Responsible Department Lead | Supporting Agencies/Departments | Estimated Cost | Potential Funding Sources | Hazards Addressed | Critical Facility Protection (Y/N) | Estimated Benefit | Source
| Assess Public and Private Dams and Develop Designs for Improvements/Replacement where Necessary | Local Plans & Regulations | Evaluate the condition of 2 public dams owned by the City. Coordinate with other public and private dam owners to help support the health and resilience of this infrastructure. | Uninitiated |  | Department of Public Works Director | DPW, United States Army Corps of Engineers, Private Dam Owners, PCCD | $ | Operating Budget; Administrative Resources | Flooding, Severe Weather | Y
| Complete Comprehensive Stormwater Management Plan | Local Plans & Regulations | The Comprehensive Stormwater Master Plan will complete Phases IV and V of the City's study of the stromwater system. |  | 2027-12-01 | Senior Stormwater & Environmental Engineer | DPW | $$ ($950000) | Capital Budget | Flooding, Severe Weather | Y |  | Carried (HMP)
| Conduct a Comprehensive Assessment of Water Resources that could Serve Framingham in the Event of Disruption from the MWRA | Local Plans & Regulations | Evaluate local water resources to serve the community and process to utilize these water bodies in crticial emergency situations to support residents. | Uninitiated |  | Director of Water & Wastewater | DPW, PCCD, MWRA | $$ |  | Drought | N
| Conduct Robust Transportation Resiliency Planning | Local Plans & Regulations | Develop a plan or ammendment to 2022 Transportation Master Plan to ensure that access is maintained in and out of the City and throughout the MetroWest region during hazard events with emphasis on facilitating emergency operations. The plan will study key junctions such as Exit 13, Exit 12, and the Route 9/126 intersection. Development of the plan will require coordination with the MWRTA and MBTA to assess the resiliency of commuter transportation. | Uninitiated | 2025-12-01 | Department of Public Works Director | Emergency Management Agency, MWRTA, MBTA | $$ |  | Flooding, Severe Weather | N
| Conduct Study of Municipal Facilities for Surge Protection | Local Plans & Regulations | The intensification of climate change impacts threatens critical local infrastructure including the electrical grid and powered devices. Disruptions to the electrical grid caused by outages (severe winds, snowstorms, flooding) and brownouts (stemming from excessive demand during extreme weather) can severly damage connected equipment and reduce or delay the ability of critical facilities to support the public. This measures invovles an analysis of critical municipal facilities for vulnerabilities and power quality needs to ensure the availability of electronics and other electrical equipment in an emergency situation. | New | 2025-12-01 | Sustainability Coordiantor | Eversource | $$ | Capital Budget | Extreme Temperatures, Severe Weather | Y |  | Sustainability Coordinator
| Develop a City-wide Business Resilience Plan to support local businesses and make the business community more resilient. | Local Plans & Regulations | Develop plan to support local businesses and make the business community more resilient. Identify business development areas where impacts from climate hazards can be easily avoided or mitigated (e.g., by avoiding floodplains or areas of known drainage-related flooding) and targeted improvements, such as a microgrid and rooftop solar installations, employed to provide extra resilience to community businesses in the Downtown and I-90 Exits 12 and 13 areas. | Uninitiated | 2026-12-01 | Director of Planning, Conservation, and Community Development | Sustainability Coordinator | $ |  | Extreme Temperatures, Flooding, Severe Weather, Drought | N
| Develop a City-wide Comprehensive Tree and Forest Management Program | Local Plans & Regulations | Development of a plan to identify, remove, and replace problem trees, preserve intact forests and street tree cover, provide guidance and resources for gradually moving toward more climate-resilient trees and forest communities (e.g. species that will tolerate warmer temperatures) and develop guidelines to manage conversion of forest land and require shade tree plantings in new developments to promote erosion control and improved infiltration. | Uninitiated | 2025-12-01 | Tree Warden | DPW, Sustainability Coordinator, PCCD | $$ |  | Extreme Temperature, Severe Weather | N
| Develop Comprehensive Plan for Beaver Management | Local Plans & Regulations | Development of a plan to mitigate against unpredictable flooding/impoundment impacts. Establish creative engineering solutions, identify suitable areas for beaver relocation or where beaver activity may be creating flood storage that contributes to resiliency, and consider the development of special legislation to give the City authority to address problematic beaver dams on private property. Evaluate permitting feasibility of beaver deceivers or other non-lethal methods to mitigating the flood impact of problem beavers in flood-prone areas. | Uninitiated |  | Director of Planning, Conservation, and Community Development | PCCD, Health Department | $ |  | Flooding, Severe Weather | Y
| Develop Hazard Mitigation Incentive Program | Local Plans & Regulations |  |  |  | Senior Stormwater & Environmental Engineer | DPW |  |  |  | N |  | Carried (HMP)
| Evaluate and Enhance Current Bylaws and Regulations Regarding Floodplain Development | Local Plans & Regulations | Review zoning bylaw, wetlands bylaw, building code, and health & safety regulations in order to ensure consistency across the regulations and most modern information is included. Could additionally leverage technical assistance via a consultant. Review Planning & Wetlands bylaws in regards to allowable development in floodplains. Currently, development is not prohibited, but mitigation is needed. Bylaw revisions need to be approved at Town Meeting. This is one of the activities to get credit for the CRS program. |  | 2025-12-01 | Senior Stormwater & Environmental Engineer | Senior Planner, Planning Board, Conservation Commission | $ |  | Flooding, Severe Weather | N |  | Carried (HMP)
| Evaluate Satellite Locations to Supplement DPW Operations Center and Salt Storage | Local Plans & Regulations | Evaluate an alternative location from Henry Street in order to provide better support City-wide and reduce response times. | In Progress | Continuous | Department of Public Works Director | DPW | N/A | N/A | Severe Weather | N
| Explore and Evaluate Means of Improving Resiliency at Historical Properties | Local Plans & Regulations | Identify opportunities to improve the resilience of municipal and private historical facilities throughout the community. | In Progress | Continuous | Director of Planning, Conservation, and Community Development | Framingham Historical Society, CPFM, Community Preservation Committee | $ | Operating Budget; Administrative Resources | Flooding, Severe Weather | N
| Integrate Flood Storage Review into Open Space Plan | Local Plans & Regulations | The City's current Open Space & Recreation Plan creates a priority list of open space parcels for the City to consider protecting from future development. Integrating flood storage capacity as a criterion in this analysis would reflect properties that would be prime candidates for increasing flood storage and mitigate flooding impacts. |  | 2025-12-01 | Senior Planner | Senior Stormwater & Environmental Engineer, Parks & Recreation Director |  | Operating Budget; FEMA Grant | Flooding | N |  | Carried (HMP)
| Integrate Relevant Hazard Mitigation Plan Priorities into Forthcoming Climate Action Plan | Local Plans & Regulations | Development of the City's first Climate Action Plan will be underway in October 2022. Integration of HMP priorities into this plan that align with emissions mitigation measures will ensure more efficient progress toward HMP implementation. | New | 2024-01-01 | Sustainability Coordiantor | Sustainability Committee, MAPC | $$ ($180,000) | Capital Budget, MAPC Technical Assistance, Executive Office of Energy and Environmental Affiars (EOEEA) Planning Assistance Grant | Extreme Temperatures, Flooding, Severe Weather, Drought | Y |  | Sustainability Coordinator
| Prepare, Adopt, Implement, and Update a Comprehensive Flood Hazard Mitigation Plan | Local Plans & Regulations | Use standard planning process (similar to the MHMP process) to develop a Comprehensive Flood Hazard Mitigation Plan. Updates would be required every 5 years. This is a minimum requirement for the CRS program for all repetitive loss communities. |  | 2027-12-01 | Senior Stormwater & Environmental Engineer | DPW | 50000 |  | Flooding | Y |  | Carried (HMP)
| Acquire 103 Guild Street Property | Natural Resouces Protection | Acquisition of a property with flood storage value for EJ neighborhood within Framingham. | In Progess | 2023-12-01 | Director of Planning, Conservation, and Community Development | Assessing Options for Grant Funding | N/A (Negotiation Underway) | SVT, CPA | Flooding | Y |  | PCCD
| Acquire the CSX Corridor and implement next steps to develop the Bruce Freeman Rail Trail at the site | Natural Resouces Protection | Purchase should be complete by October 2022. $408,000 Mass Trails grant has been received for both Bruce Freeman and Chris Walsh Trails, and NPS Grant has been acquired. Currently negotiating 3.5 miles of property and hoping to close on an acquisition in the near future. | In Progress | 2023-12-01 | Director of Planning and Community Development | PCCD | $$$ | Mass Trails Grant | Flooding | N
| Develop Plan to Implement Green Infrastructure on Municipal Properties and Along Roadways to Increase Resilience to Local Flooding | Natural Resouces Protection | Assess drainage infrastructure and drainage-driven road flooding and develop green infrastructure solutions for stormwater management to be used in tandem with improvements to the outdated and undersized stormwater system to reduce road flooding and problems with ice slicks that make roads dangerous or impassable during hazard events. Develop a list of specific priorities, assess feasibility and cost, rank priority projects in terms of climate resilience potential, and develop concept designs for key projects. For linear projects along the City’s roadways, consider utilizing green infrastructure design resources developed for other parts of the region, such as the Rhode Island Department of Transportation’s Linear Stormwater Manual, released in 2019. Framingham is participating in an MVP Project titled the Sudbury-Assabet-Concord Natural Climate Solutions Grant that will support these efforts. | In Progress |  | Department of Public Works Director | DPW, Sustainability Coordinator | $$ | Capital Budget, MVP Action Grant | Flooding, Severe Weather | Y |  | Carried (HMP) MVP Overlap
| Implement Flood Mitigation Measures in the Walnut Street Neighborhood | Natural Resouces Protection | The Walnut Street Neighborhood Flood Mitigation project will include design and permitting for wetland, stream channel, and streambank restorations to reduce flooding and increase brook capacity in the Walnut Street/Sucker Brook Drainage Area. | In Progress | 2025-12-01 | Senior Stormwater & Environmental Engineer | MVP | $$$ ($2 - 2.5 million) | MVP | Flooding | N |  | DPW
| Improve Mary Dennison Park Flood Storage | Natural Resouces Protection | The redesign of the Mary Dennision Park will preserve existing flood storage capacity located at the back of the facility and will help improve the resilience of local facilities, such as adjacent affordable housing, to flooding. | New | 2023-12-01 | Director of Parks and Recreation | Mass DEP | $$$ ($20 - $25 million) | Mary Dennison Settlement and Town Meeting / City Appropriation | Flooding | Y |  | PCCD
| Restore Wetlands and Conduct Associated Ecological Restoration to Increase Local Flood Storage and Improve Water Quality | Natural Resouces Protection | City is pursuing conditions assessment and potential wetlands restoration to improve water quality at a Lake Waushakum outfall. |  |  | Director of Planning and Community Development | DPW | $$ | Capital Budget, MVP Action Grant | Flooding, Severe Weather | N |  | Carried (HMP)
| Foster an Improved Communications Network to Better Reach Vulnerable Populations and those Most in Need of Information and Assistance | Outreach & Education | Identify vulnerable populations and foster an improved communications network in advance of a hazard event to facilitate communication efforts and outreach to those most in need of information and assistance. Expand upon current efforts to strengthen relationships with Framingham's Environmental Justice neighborhoods. | In Progress | Continuous | Sustainability Coordinator | Emergency Management Agency | $ | Operating Budget; MAPC Technical Assistance | Extreme Temperatures, Flooding, Severe Weather, Drought | N
| Align Capital Projects in EJ Neighborhoods to Advance Climate Resiliency | Outreach & Education | Departments will use design features that reduce the risk of climate change on EJ communities for construction projects. CDBG funding could be a tool for departments and local neighborhoods to advance such measures. | New | Continuous | Community Development Coordinator | Sustainability Coordinator |  | CDBG funds | Extreme Temperatures, Flooding, Severe Weather, Drought | N |  | CBDG
| Coordinate Local Community Organizations to Develop Educational Messaging and/or Programming to Transfer Climate Change Risk and Vulnerability Knowledge to the General Public | Outreach & Education | Communicate with Framingham State University, Mass Bay Community College, and other local organizations to increase awarness of climate change risks. | In Progress | Continuous | Sustainability Coordiantor | PCCD, DPW, Sustainability Committee | N/A | N/A | Extreme Temperatures, Flooding, Severe Weather, Drought | N
| Coordinate Regional Management Efforts of Lake Cochituate | Outreach & Education | including studying ways to reduce pesticide and nutrient inputs from stormwater runoff. |  | Continuous |  | Mass DCR, Town of Natick, Town of Wayland |  |  | Extreme Temperatures | N
| Develop Green Infrastructure Marketing/Education Program to Business Community | Outreach & Education | Develop green infrastructure marketing/education program to business community. Could additionally leverage technical assistance via a consultant. Note: the NPDES MS4 permit will require the Town to provide public education to businesses, institutions, commercial facilities, and developers. |  | 2026-12-01 | Senior Stormwater & Environmental Engineer | DPW, Sustainability Coordinator | $ | Operating Budget | Flooding, Extreme Heat | N |  | Carried (HMP)
| Expand Outreach on Water Conservation | Outreach & Education | Expand water conservation efforts for Framingham residents and businesses to mitigate consumption of MWRA and local well water. | Uninitiated |  | DPW | Massachusetts Water Resource Authroity (MWRA), Sustainability Coordinator | $ |  | Drought | N
| Facilitate Education for Prospective Homebuyers and Realtors to Address Flood Risks | Outreach & Education | Provide education to make sure that buyers are aware of what it means to purchase a home that may be located in or near a floodplain and educate residents on protections such as flood insurance that can mitigate financial risks associated with climate hazards. Target landlord associations and realtors to encourage risk communication. | Uninitiated | 2025-12-01 | Senior Stormwater & Environmental Engineer | DPW, Sustainability Coordinator, PCCD | $ | Operating Budget | Flooding | N
| Maximize Local Energy Efficiency to Reduce Stress on Grid Demand During Peak Usage & Improve Passive Survivability of Facilities | Outreach & Education | The intensification of climate change impacts threatens critical local infrastructure including the electrical grid and powered devices. Energy efficient, well-insulated buildings can maintain habitable conditions for longer durations during prolonged utility outages. |  | Continuous | Sustainability Coordiantor | Mass Save, Eversource, Town of Natick | $$ | Mass Save (Eversource), U.S. Department of Housing and Urban Development Technical Assistance | Extreme Temperatures | Y |  | Carried (MVP)
| Partner with Local Utility on Climate Resilience Efforts | Outreach & Education | Enhance coordination to identify and address vulnerabilities in utility infrastructure and enhance communication and cooperation between the City and private utilities. | In Progress | Continuous | Sustainability Coordinator | DPW, CPFM, Schools | N/A | N/A | Extreme Temperatures, Flooding, Severe Weather, Drought | N
| Plan and Post Neighborhood and Regional Evacuation Routes | Outreach & Education |  | Uninitiated |  | Director of the Emergency Management Agency |  | $$ |  | Flooding, Severe Weather | N
| Reimplement Rain Barrel Program for Residents | Outreach & Education | A program that was previously offered to residents that offered discounted rain barrels and that promoted better stromwater management. |  | 2024-12-01 | Department of Public Works Director | Sustainability Coordinator | $ | MassDEP | Flooding, Drought | N |  | Carried (HMP)
| Continue to Support Coordinated Efforts to Provide Emergency Shelters | Structure & Infrastructure | Provide shelters that that effectively serve Framingham’s population during hazard events, including cooling and warming centers. | In Progress | Continuous | Framingham Public Schools Director of Buildings and Grounds, Director of Capital Projects and Facilities Management | DPW, CPFM, FPS | $ | Operating Budget; Administrative Resources | Extreme Temperatures, Flooding, Severe Weather, Drought | Y
| Evaluate Opportunities to Use Clean Energy Assets (Including Microgrids) to Provide Enhanced Backup Power to Critical Facilities | Structure & Infrastructure | Explore the implementation of solar PV, battery storage, and other renewable energy technologies to provide clean energy resilience to critical municipal facilities. | In Progress | 2025-12-01 | Sustainability Coordiantor | Capital Projects and Facilities Management, DPW, Framingham Public Schools | $ | MassCEC Grant, Capital Budget, Power Purchase Agreement Financing | Severe Weather, Flooding, Extreme Temperatures | Y
| Implement Drainage Improvements on Roadways to Reduce Flooding Risks | Structure & Infrastructure | Fountain Street - Comprhensive improvements to the Fountain Street intersection are underway. This project includes drainage improvements that will benefit the water quality of Farm Pond. Easement acquisitions will take place this year, along with utility pole installation and overhead wire transfers. Funding sources for the final design and construction are being reviewed. Nobscott Area - Drainage improvements are in the process of being implemented as part of local development of the Nobscott Plaza. DPW also previously made improvements to stormwater infrastructure for Fire Station #7." |  |  | Director of Highway and Sanitation | Senior Stormwater & Environmental Engineer | $$$ |  | Flooding, Severe Weather | Y |  | Carried (HMP)
| Implement Emergency Generators for Traffic Signals | Structure & Infrastructure | Power can be lost during winter storm events or high winds, including power used for traffic signals. For example, during a 2013 storm event, power was lost at a major intersection's traffic signal for 6 days. Police details were required, pulling limited emergency personnel from other weather-related emergencies. Loss of power to traffic signals compounds hazardous travel conditions. Emergency, back-up generators for traffic signals will help facilitate traffic flow and mitigate hazardous conditions. |  |  | Department of Public Works Director | DPW | 10000 | Capital Funding | Severe Weather | N |  | Carried (HMP)
| Implement Recommendations from the Feasibility Study for Removal of Landham Pond Dam | Structure & Infrastructure |  | Uninitiated | Contingent on Acquisition of CSX Property | DPW | PCCD |  | $$$ | Flooding, Severe Weather | N
| Install additional stream gauges and Web-based Public Portal for Stream Gauge Data | Structure & Infrastructure | "Install additional automated stream gauges (surface water level sensors and communications equipment) at high risk areas. Angelica Drive (Angelica Brook) Bates Rd (Beaver Dam Brook)" |  | 2025-12-01 | Department of Public Works Director | DPW | $15,000-$30,000/each | Capital Funding; FEMA Grant | Flooding, Severe Weather, Drought | N |  | Carried (HMP)
| Overhaul HVAC in Schools that Currrently Lack Air Conditioning | Structure & Infrastructure | Implementation of energy efficient AC systems to provide relief to students and faculty from rising summer temperatures. Schools currently without full air conditioning solutions include Brophy Elementary School, Dunning Elementary School, Hemenway Elementary School, McCarthy Elementary School, Potter Road Elementary School, Stapleton Elementary School, and Walsh Middle School. | In Progress | 2029-06-01 | Director of Buildings and Grounds | Schools | $$$ | Eversource, Green Communities Competitive Grants, Capital Budget, ARPA | Extreme Temperatures | Y
| Promote Cool Roof Designs, Rooftop Renewable Energy Systems, Green Infrastructure to Mitigate Heat Island Impacts | Structure & Infrastructure | Educate the public about cool roofs and green roofs that help residents better manage extreme temperatures within local buildings. | New | January 2023 - Continuous | Sustainability Coordiantor | Department of Public Works, Department of Planning and Community Development | $ | Capital Budget, MAPC, Department of Housing and Urban Development Technical Assistance | Extreme Temperatures | N |  | Sustainability Coordinator
| Protect or Acquire Private Property Impacted by Flooding in Repetitive Loss Neighborhoods | Structure & Infrastructure | Hemenway - Efforts will be supported by an MVP Action Grant regarding removal of Landham Pond Dam which is tied to acquisition of the rail trail property. Auburn - In order to mitigate this problem, the City decided to install two backflow preventers, a component of which is a “duckbill” style check valve. 3 out of 4 duckbill devices were allowed for installation. Beaver Dam Brook - Acquisition of 103 Guld Street will support will help alleviate flooding issues in this neighborhood. Walnut Street - Identify, acquire, and/or relocate flood-prone buildings so that they are out of the floodplain. Place restrictions on purchased land in floodplain to prevent future development. Identify and protect existing flood-prone buildings by floodproofing, elevation, or minor structural projects. Assume 171, 175, & 179 Walnut Street. Potentially more properties on eastern side of Walnut Street. In August 2021, the City of Framingham received a $269,030 Municipal Vulnerability Preparedness (MVP) Action Grant from the Baker-Polito Administration to support the project. In February 2020, the City received a $206,850 MVP Action Grant from the Baker-Polito Administration to support the project. | In Progress |  | Director of Planning and Community Development | DPW | $$$ | Capital Budget, MVP Action Grant | Flooding, Severe Weather | N |  | Carried (HMP)
| Purchase & Install 4 Automated Weather Stations and Additional Pavement Sensors | Structure & Infrastructure | Purchase and install 4 automated weather stations throughout Town, with web-based access. Weather stations will assist DPW personnel with assessing storms to improve response to extreme precipitation, high winds, and winter storms. They will also assist Police & Fire with emergency response for storm events. The DPW Highway Department use pavement sensors to evaluate the temperature of pavement during cold weather. This data enables the Highway Department to identify roads for pretreatment which reduces roadway icing and other hazards associated with winter storms. |  | 2025-12-01 | Senior Stormwater & Environmental Engineer | Department of Public Works, Police Department, Fire Department | $10,000+ | Operating Budget; FEMA Grant | Extreme Temperatures, Flooding, Severe Weather, Drought | Y |  | Carried (HMP)
| Rehabilitate Worcester Road Sewer Pump Station | Structure & Infrastructure | Rehabilitation of the Worcester Road Pump Station is underway. |  | 2026-12-01 | Director of Water & Wastewater | DPW | $$$ | Capital Budget, MassDEP State Revolving Loan Program | Flooding, Severe Weather | Y |  | Carried (HMP)
| Replace School Street, Taralli Terrace, and Second Street Bridges | Structure & Infrastructure | School Street - Highlighted as part of a recent visit by U.S. House Assistant Speaker to highlight need for infrastructure funding. Framingham anticipating pursuing grant funding for this measure. Currently highest priority bridge replacement project. Taralli Street - Evaluation of bridge on CIP for 2025 request. Second Street - Evaluation of bridge on CIP for 2025 request. |  |  | City Engineer |  | $$$ (Taralli and Second Street Bridge Replacement Evaluations $200,000) |  | Flooding, Severe Weather | Y |  | Carried (HMP)
| Retrofit and Rehabilitate Existing Culverts to Handle Increased Volumes of Stormwater | Structure & Infrastructure | "Fuller School pedestrian path - ""No updates on this specific action. Stormwater improvements related to new school have significantly reduced impervious surface area in the neighborhood (a reduction of about 1/4 impervious surface). Several culvert retorfits included under this work and areas behind Fuller School with underground chambers for stormwater management. Drainage improvements at the site may have alleviated the issues here. Challenges with sewer infrastructure may complicatethis project. Culvert and trench need to be evaluated for retrofit. "" An emergency repair to the culvert was completed in 2021. Nobscott Intersection Project currently in progress with construction underway as of March. More information avialable here: https://www.framinghamma.gov/2314/Nobscot-Intersection-Improvements. Hop Brook - DPW secured $150K DER grant funding to study the replacement of the City-owned Colonial Drive culvert which is the last culvert downstream of the CSX culverts and will need to be upgraded before the CSX culverts can be upgraded. Anticipated June 2019" |  |  | Director of Highway and Sanitation | DPW | $$$ |  | Flooding, Severe Weather | Y |  | Carried (HMP)
| Retrofit, Update, and Replace Culverts as Neccessary to Local Increase Stormwater Capacity | Structure & Infrastructure | Implement improvements for or replacements of the Fuller Middle School Pedestrian Path Culvert, Edmands Road Culvert, and CSX Hop Brook Culvert to improve local capacity for increased stormwater flow. |  | 2030-12-01 | Director of Highway and Sanitation | DPW | $$$ ($1.5 million +) | Capital Funding; FEMA Grant; MVP Action Grants | Flooding, Severe Weather | Y |  | Carried (HMP)
Note on C1: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Types: Local Plans & Regulations, Structure and Infrastructure, natural resources protection, and education & outreach.
Note on B24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Flagged for removal and integration as part of the broader plan discussion.

## Data Validation List (hidden)
Local Plans & Regulations
Structure & Infrastructure
Natural Resouces Protection
Outreach & Education

## Dropdown Lists (hidden)
Mitigation Goals
TBD
TBD
TBD
TBD
TBD
Mitigation Category
Local Plans & Regulations
Structure & Infrastructure Projects
Natural Systems Protection
Education & Awareness Programs
Emergency Preparedness
Priority
Very High
High
Medium
Low
Project Status
Completed
Completed & Expanded Upon
In Progress
Delayed
Unknown
Continuous
Cancelled
Keep for Updated Plan?
YES - updated/revised description provided at right, if applicable
NO - explanation provided at left

## Framingham's 2022 Attempt (hidden)
# | Mitigation Measure | TOTAL SCORE | Description | Implementation Timeline | Responsible Department | Supporting Agencies/Departments | Estimated Cost | Potential Funding Sources | Hazards Addressed
1 | Evaluate current bylaws and regulations regarding floodplain development to ensure they are consistent and updated | 28.4
2 | Purchase & install 4 automated weather stations | 27.6
3 | Integrate flood storage review into open space plan | 27.4
4 | Install additional stream gauges | 26.8
5 | Enhance current bylaws and regulations to prevent future development in the floodplain | 26.8
6 | Install additional pavement sensors | 26.4
7 | Develop stormwater bylaw & regulations | 26.4
8 | Develop green infrastructure bylaw & regulations | 26.2
9 | Emergency generators for traffic signals | 26.2
10 | Conduct a Climate Change Vulnerability Assessment | 26
11 | Culvert replacement at CSX crossing of Hop Brook | 26
12 | Prepare, adopt, implement, and update a comprehensive flood hazard mitigation plan | 26
13 | Complete Stormwater Master Plan Phase IV | 25.8
14 | Complete Stormwater Master Plan Phase V | 25.8
15 | Develop green infrastructure marketing/education program to business community | 25.8
16 | Construct Walnut Street Sewer Pump Station | 25.4
17 | Nobscot Fire Station Area Drainage Improvements | 25.4
18 | Web based public portal for stream gauge data | 25
19 | School Street bridge replacement | 24.6
20 | CRS program assessment | 24.4
21 | Fountain Street Drainage Improvement | 24.2
22 | Expand rain barrel program | 24
23 | Taralli Terrace Bridge replacement | 24
24 | Second Street Bridge replacement | 24
25 | Replace Farm Pond outfall | 23.8
26 | Culvert retrofit at Fuller School pedestrian path | 23.8
27 | Emergency generators for general store | 23.6
28 | Woodfield Playground infiltration system | 23.2
29 | Install green infrastructure in the vicinity of Butterworth Park | 23
30 | Develop hazard mitigation incentive program | 23
31 | Constructed wetlands or wetlands restoration project | 23
32 | Flood Protection of private property with flood loss in Hemenway neighborhood | 22.8
33 | Flood Protection of private property with repetitive loss in Auburn Street neighborhood | 22.8
34 | Flood Protection of private property with repetitive loss in Circle Drive neighborhood | 22.8
35 | Flood Protection of private property with repetitive loss in Prescott St neighborhood | 22.8
36 | Develop and implement a residential rain garden program | 22.6
37 | Charlotte Dunning School green infrastructure | 22.6
38 | Edmands Road culvert upgrade | 22.4
39 | Install beaver deceivers near pedestrian bridge near high school | 21.4
40 | Flood Protection of Town Buildings | 21
41 | Acquisition and Relocation or flood protection of private properties with repetitive loss in Beaver Dam Brook neighborhood | 20.6
42 | Acquisition and Relocation or flood protection of private properties with repetitive loss in Walnut Street neighborhood | 20.2
43 | Rehabilitate flood control berm at Callahan Senior Center | 20
44 | Acquisition and Relocation or flood protection of private properties with repetitive loss in Auburn Street neighborhood | 19.8
45 | Relocation of Town Buildings out of floodplain | 17.8